## Rundown
Instalasi KDS di Store …
No. |  |  | Activity | Start & Estimasi | PIC | Notes | Paraf
A |  |  | SEBELUM INSTALASI
| 1 |  | Backup DB POS Terakhir
|  |  | Copy ke Flash Disk & PC Office C:\BackupDB\POSxxx.bak | 22:00
B |  |  | PROSES INSTALASI
| 1 |  | Instalasi Black Box KDS | 22:15 |  | Setting Black Box dilakukan Di KP
|  | i | Instalasi KDS Rebusan, Gorengan, Take Out & Expo | 45 menit
|  | ii | Set IP KDS Rebusan : 192.168.xx.71 (xx : sesuai segmen IP store)
|  | iii | Set IP KDS Gorengan : 192.168.xx.72 (xx : sesuai segmen IP store)
|  | iv | Set IP KDS Take Out : 192.168.xx.73 (xx : sesuai segmen IP store)
|  | v | Set IP KDS Expo : 192.168.xx.74 (xx : sesuai segmen IP store)
| 2 |  | Setting DB POS Untuk KDS |  |  | * Konfigurasi dilakukan di KP via HQ *Config lihat sheet : Config DB POS KDS
|  | i | Sales Type
|  | ii | System RVC Option Bit
|  | iii | System Option Bit
|  | iv | PC Table Type Def
|  | v | PC Table Device Mask
|  | vi | TS Config
|  | vii | Kitchen Printer
|  | viii | Remove Button POS
|  | ix | Menu Item
| 3 |  | Hotfix semua POS ke versi 117 | 23:00
|  | i | Copy file & folder hotfix, paste di C:\DTSPOS\ & C:\DTSPOS\POS | 2 menit
|  | ii | Jalankan file hotfixPOS.bat | 3 menit
|  | iii | Buka CMD, mainmenu f=1 | 3 menit
|  | iv | Copy Prtmgt.dll ke C:\DTSPOS\ & C:\DTSPOS\POS | 2 menit |  | Pastikan file tsb Last Modified 3 Juli 2016
| 4 |  | Install Aplikasi KDS di POS-01 | 23:30
|  | i | Install KDS.exe | 3 menit
|  | ii | Buka RDS Console, Auto Search KDS Console | 3 menit
|  | iii | Copy DB KDS (Bakmi GM - KDS) dari Flash Disk ke C:\QSRAuto\KDS\Data | 2 menit
|  | iv | Buka Apps KDS Builder Pro, Load DB "Bakmi GM KDS" | 2 menit
Copy Curret data to Runtime Directory
C |  |  | SETELAH INSTALASI
| 1 |  | Backup DB POS | 0:00
|  | i | Rename DB terakhir menjadi C:\BackupDB\POSxxx_before.bak | 3 menit
|  | ii | Backup DB, Copy ke C:\BackupDB\POSxxx.bak | 2 menit
| 2 |  | Test Posting | 0:05
|  | i | Test posting KDS menggunakan panduan pada sheet Test KDS | 30 menit
| 3 |  | Rekap Hasil Test
|  | i | Listing Hasil test untuk dilakukan perbaikan | 10 Menit
| 4 |  | Revisi Configurasi
|  | i | Restore DB POS poin C.1 | 5 menit
|  | ii | Setting perbaikan yang sudah direkap | 15 menit
|  | iii | Backup DB setelah revisi | 5 menit
| 5 |  | Test Posting
|  | i | Test ulang posting setelah revisi | 30 menit
|  | ii | Jika sudah tidak ada kekurangan lanjut ke tahap berikutnya
| 6 |  | Restore DB setelah post testing | ~
|  | i | Restore DB C:\BackupDB\POSxxx.bak | 5 menit
| 7 |  | Backup Database | ~
|  | i | Backup DB POS ke Flash Disk | 3 menit
|  | ii | Backup DB KDS ke Flash Disk | 2 menit

## Config DB POS KDS
CONFIG DB POS UNTUK KDS
No. | Feature | Changes | Screen Capture | Status
1 | Sales Type | Ubah type def TDEF : 804400
| Dine In, Ultah DI, Fieldtrip DI menggunakan Tray | √ option bit 1,10,14
2 | System RVC Option Bit | √ option bit 4,7,10,11,14,16,20,21,22,23,24,25,26,31,33,34,36,39,42,43,44,50,52,53,54,55,56,57,61,66,67,68,71,72,74,77,85,88,89,91,94,97,100,110,111,120,151,154,155,182,185,213
3 | System Option Bit | √ option bit 1,3,4,5,12,53,197,211
4 | PC Table Type Def | √ option bit 1,6,15
5 | PC Table Device Mask | POS-01 : √ option bit 11,31,41,42
POS-02 : √ option bit 12,31,41,42
POS-03 : √ option bit 13,32,41,42 *Disesuaikan
6 | TS Config - 2 TBL_LAYOUT_GSM-S01 (Take Out Button) | Type : 18 Macro, Obj Num : 161 Take Out, Next Screen : 2 TBL_Layout_takeout
| Macro - 161 Take Out | 1. 91 Function - Keyboard : 12 Clear 2. 92 Function - Touchscreen : 9 TS Next Screen 3. 19 Sales Type Object Number : 2 Take Out 4. 20 Trans Type Object Number : 2 Take Out
7 | TS Config - 1 MENU MAIN MAKANAN-REG | Type : 9 Menu Item SLU Group Obj Num : 81 INFO Next Screen : 1 MENU MAIN MAKANAN-REG
8 | Kitchen Printer | Name : 41 Rebusan TDEF : 000868600000 Printer : 33 KDS Backup Printer : 45 Backup Name : 42 Gorengan TDEF : 000868600000 Printer : 33 KDS Backup Printer : 45 Backup Name : 45 Backup TDEF : 058400600000 Printer : 11 RKP FOOD 01 Backup Printer : 12 RKP FOOD 02
9 | Menu Item | 1. Detail 1 (Name 2) 2. Detail 3 (KDS Colour & Tray) 3. Type Def (Option Bit 58 ON) 4. Tax & Printer (Rebusan & Gorengan ON) | Configuration : See Attachment
10 | Remove Button POS | 1. Remove Move Table 2. Remove Overring Check
11 | Add Button Tambah | Type : 1. Menu Item Obj Number Obj Num : 9091001 * TAMBAH * Tambahkan pada : 1. MENU MAIN EMPL MEAL . . (sampai dengan) . 1 MENU MAIN PROMO ULTAH

## Scenario Testing
SKENARIO TESTING KDS
No. | 1 | No. | 3 | No. | 5 | No. | 7
Materi | Menu Reguler | Materi | Menu Paket | Materi | Void Check | Materi | Condiment
Transaksi | DINE IN | Transaksi | DINE IN | Transaksi | TAKE OUT | Transaksi | Dine In
Menu Pesanan | Nasi Goreng Special (tidak bakso ikan, tidak udang) Brokoli Sapi Lada Hitam (tidak wortel, tidak brokoli) Nasi Putih ½ Pangsit Kuah 2 Es Teh Manis | Menu Pesanan | 3 Paket Berkat A 2 Reward E 3 Aqua | Menu Pesanan | 4 Bakmi Sapi Lada Hitam 2 Pangsit Goreng | Menu Pesanan | 2 Nasi Goreng (Tdk Baso Ikan, Tidak Kol, Extra Acar, Sedikit Minyak) 4 Bakmi GM (Extra Kuah, Yamin) 6 Es The Manis
Aktivitas | - Kirim Dapur - Bayar Cash | Aktivitas | - Bayar Cash | Aktivitas | - Kirim Dapur - Void Check (Terlalu Lama) | Aktivitas | - Kirim Dapur - Void 4 Bakmi GM - Posting 2 Bakmi GM (Extra Kuah, Yamin, Patas) - Posting 2 Bakmi A (Extra Kuah, Tidak Sayur, Patas) - Kirim Dapur - Posting 2 Bakmi Masak (Tidak Sayur, Tidak Ayam, Tambah) - Kirim Dapur
Catatan |  | Catatan |  | Catatan |  | Catatan
No. | 2 | No. | 4 | No. | 6 | No. | 8
Materi | Menu Reguler | Materi | Void Item | Materi | Void Check | Materi | Tray
Transaksi | DSO - 201609290155 | Transaksi | DINE IN | Transaksi | DINE IN | Transaksi | Ultah DI
Menu Pesanan | 5 Mie Goreng (Extra Sambal) 5 Bakmi GMB (Yamin, Pisah) 5 Pangsit Goreng (PLDL, Extra Saos PS) | Menu Pesanan | 3 Bakmi Goreng 2 Nasi GMB 2 Pangsit Goreng 5 Fruit Punch | Menu Pesanan | 1 Bakmi ALC 2 Nasi GM 1 Es Lemon Tea 2 Teh Manis | Menu Pesanan | 50 Bakmi GM
Aktivitas | - Kirim Dapur - Bayar Cash | Aktivitas | - Kirim Dapur - Void 2 Pangsit Goreng - Posting 1 Pangsit Goreng (Patas) - Void 2 Fruit Punch - Posting 2 Es Tawar (Patas) | Aktivitas | - Kirim Dapur - Void Bakmi ALC - Void 1 Es Lemon Tea - Kirim Dapur - Void Check (Menu Habis) | Aktivitas | - Kirim Dapur - 20 Bakmi Goreng SPC (Tambah) - Kirim Dapur
Catatan |  | Catatan |  | Catatan |  | Catatan

## Master Data KDS
Tray Requirement
Number (PLU) | Complete Name / Name 3 (Max 25 chars) | Length Complete name | Name 1 (Max 16 chars) | Length Alias Name | Name 2 (Max 6 chars) | Length KDS Display | mg | Major Grop | fg | Family Group | rg | Report Group | Printer | KDS Colour | Priority | Item Line Group | Notes | Tray Requirement | Refrensi Hal | Wadah | Tray | TO | DS | CDI | CTO | CDS | BtDI | BtTO | PDI | PTO | UDI | UTO | UDS | FDI | FTO | BzDI | BzTO | ADV
1011001 | BAKMI AYAM | 10 | BAKMI A | 7 | B A | 3 | 10 | #REF! | 11 | #REF! | 11 | #REF! | REBUSAN | 5 Menit |  | BAKMI |  | 4 | 11 | Mangkuk | 4 | X | X | Delete | Delete | Delete | Delete | Delete | X | X | 4 | X | X | 4 | X | Delete | Delete | Tidak ke KDS
1011002 | BAKMI BASO | 10 | BAKMI B | 7 | B B | 3 | 10 | #REF! | 11 | #REF! | 11 | #REF! | REBUSAN | 5 Menit |  | BAKMI |  | 4 |  | Mangkuk | 4 | X | X | Delete | Delete | Delete | Delete | Delete | X | X | 4 | X | X | 4 | X | Delete | Delete | Tidak ke KDS
1011003 | BAKMI PANGSIT | 13 | BAKMI P | 7 | B P | 3 | 10 | #REF! | 11 | #REF! | 11 | #REF! | REBUSAN | 5 Menit |  | BAKMI |  | cek |  | Mangkuk | 4 | X | X | Delete | Delete | Delete | Delete | Delete | X | X | 4 | X | X | 4 | X | Delete | Delete | Tidak ke KDS
1011004 | BAKMI PANGSIT GORENG | 20 | BAKMI PG | 8 | B PG | 4 | 10 | #REF! | 11 | #REF! | 11 | #REF! | REBUSAN | 5 Menit |  | BAKMI |  | cek |  | Mangkuk | 4 | X | X | Delete | Delete | Delete | Delete | Delete | X | X | 4 | X | X | 4 | X | Delete | Delete | Tidak ke KDS
1011005 | BAKMI SPECIAL GM | 16 | BAKMI GM | 8 | B GM | 4 | 10 | #REF! | 11 | #REF! | 11 | #REF! | REBUSAN | 5 Menit |  | BAKMI |  | 4 | 26 | Mangkuk | 4 | X | X | Delete | Delete | Delete | Delete | Delete | X | X | 4 | X | X | 4 | X | Delete | Delete | Tidak ke KDS
1011006 | BAKMI SPECIAL GM BASO | 21 | BAKMI GMB | 9 | B GMB | 5 | 10 | #REF! | 11 | #REF! | 11 | #REF! | REBUSAN | 5 Menit |  | BAKMI |  | cek |  | Mangkuk | 4 | X | X | Delete | Delete | Delete | Delete | Delete | X | X | 4 | X | X | 4 | X | Delete | Delete | Tidak ke KDS
1011007 | BAKMI SPECIAL GM PANGSIT | 24 | BAKMI GMP | 9 | B GMP | 5 | 10 | #REF! | 11 | #REF! | 11 | #REF! | REBUSAN | 5 Menit |  | BAKMI |  | 4 | 18 | Mangkuk | 4 | X | X | Delete | Delete | Delete | Delete | Delete | X | X | 4 | X | X | 4 | X | Delete | Delete | Tidak ke KDS
1011008 | BAKMI SPECIAL GM PNGST GR | 25 | BAKMI GMPG | 10 | B GMPG | 6 | 10 | #REF! | 11 | #REF! | 11 | #REF! | REBUSAN | 5 Menit |  | BAKMI |  | 4 | 21 | Mangkuk | 4 | X | X | Delete | Delete | Delete | Delete | Delete | X | X | 4 | X | X | 4 | X | Delete | Delete | Tidak ke KDS
1011010 | BAKMI GORENG | 12 | BAKMI GR | 8 | BG | 2 | 10 | #REF! | 11 | #REF! | 12 | #REF! | GORENGAN | 8 Menit |  | BAKMI GRG |  | cek |  | Piring | 3 | X | X | Delete | Delete | Delete | Delete | Delete | X | X | 3 | X | X | 3 | X | Delete | Delete | Tidak ke KDS
1011011 | BAKMI GORENG SPECIAL | 20 | BAKMI GR SPC | 12 | BG+ | 3 | 10 | #REF! | 11 | #REF! | 12 | #REF! | GORENGAN | 8 Menit |  | BAKMI GRG |  | cek |  | Piring | 3 | X | X | Delete | Delete | Delete | Delete | Delete | X | X | 3 | X | X | 3 | X | Delete | Delete | Tidak ke KDS
1011012 | BAKMI MASAK | 11 | BAKMI MS | 8 | B MS | 4 | 10 | #REF! | 11 | #REF! | 12 | #REF! | GORENGAN | 8 Menit |  | BAKMI PLS |  | 3 | 33 | Mangkuk Besar | 2 | X | X | Delete | Delete | Delete | Delete | Delete | X | X | 2 | X | X | 2 | X | Delete | Delete | Tidak ke KDS
1011013 | BAKMI CAH JAMUR | 15 | BAKMI CJ | 8 | B CJ | 4 | 10 | #REF! | 11 | #REF! | 12 | #REF! | GORENGAN | 8 Menit |  | BAKMI PLS |  | cek |  | Piring | 3 | X | X | Delete | Delete | Delete | Delete | Delete | X | X | 3 | X | X | 3 | X | Delete | Delete | Tidak ke KDS
1011014 | BAKMI DAGING CAH CABAI | 22 | BAKMI DCB | 9 | B DCB | 5 | 10 | #REF! | 11 | #REF! | 12 | #REF! | GORENGAN | 8 Menit |  | BAKMI PLS |  | cek |  | Piring | 3 | X | X | Delete | Delete | Delete | Delete | Delete | X | X | 3 | X | X | 3 | X | Delete | Delete | Tidak ke KDS
1011015 | BAKMI CAP CAY | 13 | BAKMI CAP | 9 | B CAP | 5 | 10 | #REF! | 11 | #REF! | 12 | #REF! | GORENGAN | 8 Menit |  | BAKMI PLS |  | cek |  | Piring | 3 | X | X | Delete | Delete | Delete | Delete | Delete | X | X | 3 | X | X | 3 | X | Delete | Delete | Tidak ke KDS
1011016 | BAKMI AYAM CAH CABAI | 20 | BAKMI ACB | 9 | B ACB | 5 | 10 | #REF! | 11 | #REF! | 12 | #REF! | GORENGAN | 8 Menit |  | BAKMI PLS |  | cek |  | Piring | 3 | X | X | Delete | Delete | Delete | Delete | Delete | X | X | 3 | X | X | 3 | X | Delete | Delete | Tidak ke KDS
1011018 | YI FU MIE | 9 | YI FU MIE | 9 | YFM | 3 | 10 | #REF! | 11 | #REF! | 12 | #REF! | GORENGAN | 8 Menit |  |  |  | 3 | 37 | Piring | 2 | X | X | Delete | Delete | Delete | Delete | Delete | X | X | 2 | X | X | 2 | X | Delete | Delete | Tidak ke KDS
1011020 | BAKMI DOANK | 11 | BAKMI DOANK | 11 | B DNK | 5 | 10 | #REF! | 11 | #REF! | 11 | #REF! | REBUSAN | 5 Menit |  | BAKMI |  | 4 | 8 | Mangkuk | 4 | X | X | Delete | Delete | Delete | Delete | Delete | X | X | 4 | X | X | 4 | X | Delete | Delete | Tidak ke KDS
1011022 | BAKMI BROKOLI SAPI LD HTM | 25 | BAKMI BSLH | 10 | B BSLH | 6 | 10 | #REF! | 11 | #REF! | 12 | #REF! | GORENGAN | 8 Menit |  | BAKMI PLS |  | 3 | 15 | Piring | 3 | X | X | Delete | Delete | Delete | Delete | Delete | X | X | 3 | X | X | 3 | X | Delete | Delete | Tidak ke KDS
1011023 | BAKMI AYAM LADA CHA CHA | 23 | BAKMI ALC | 9 | B ALC | 5 | 10 | #REF! | 11 | #REF! | 11 | #REF! | REBUSAN | 5 Menit |  | BAKMI |  | cek |  | Piring | 3 | X | X | Delete | Delete | Delete | Delete | Delete | X | X | 3 | X | X | 3 | X | Delete | Delete | Tidak ke KDS
1011024 | YI FU MIE NI | 12 | YF MIE-NI | 9 | YFM-NI | 6 | 10 | #REF! | 11 | #REF! | 12 | #REF! | GORENGAN | 8 Menit |  |  |  | cek |  | Piring | 3 | X | X | Delete | Delete | Delete | Delete | Delete | X | X | 3 | X | X | 3 | X | Delete | Delete | Tidak ke KDS
1011025 | BAKMI AYAM SAUS THAI | 20 | BAKMI AT | 8 | B AT | 4 | 10 | #REF! | 11 | #REF! | 12 | #REF! | GORENGAN | 8 Menit |  | BAKMI PLS |  | cek |  | Piring | 3 | X | X | Delete | Delete | Delete | Delete | Delete | X | X | 3 | X | X | 3 | X | Delete | Delete | Tidak ke KDS
1011026 | BAKMI KUAH CHA CHA | 18 | BAKMI KUAH C | 12 | B KC | 4 | 10 | #REF! | 11 | #REF! | 11 | #REF! | REBUSAN | 5 Menit |  | BAKMI |  | #REF! | 32 | Mangkuk | 4 | X | X | Delete | Delete | Delete | Delete | Delete | X | X | 4 | X | X | 4 | X | Delete | Delete | Tidak ke KDS
1011027 | YF MIE NI ACB | 13 | YF MIE-NI ACB | 13 | YFN ACB | 7 | 10 | #REF! | 11 | #REF! | 12 | #REF! | GORENGAN | 8 Menit |  |  |  | 3 | 37 | Piring | 3 | X | X | Delete | Delete | Delete | Delete | Delete | X | X | 3 | X | X | 3 | X | Delete | Delete | Tidak ke KDS
1012001 | BIHUN AYAM | 10 | BIHUN A | 7 |  | 0 | 10 | #REF! | 12 | #REF! | 11 | #REF! | REBUSAN | 5 Menit | [5 empty] | Mangkuk | 4 | [9 empty] | 4 |  |  | 4
1012002 | BIHUN BASO | 10 | BIHUN B | 7 |  | 0 | 10 | #REF! | 12 | #REF! | 11 | #REF! | REBUSAN | 5 Menit | [5 empty] | Mangkuk | 4 | [9 empty] | 4 |  |  | 4
1012003 | BIHUN PANGSIT | 13 | BIHUN P | 7 |  | 0 | 10 | #REF! | 12 | #REF! | 11 | #REF! | REBUSAN | 5 Menit | [5 empty] | Mangkuk | 4 | [9 empty] | 4 |  |  | 4
1012004 | BIHUN PANGSIT GORENG | 20 | BIHUN PG | 8 |  | 0 | 10 | #REF! | 12 | #REF! | 11 | #REF! | REBUSAN | 5 Menit | [5 empty] | Mangkuk | 4 | [9 empty] | 4 |  |  | 4
1012005 | BIHUN SPECIAL GM | 16 | BIHUN GM | 8 |  | 0 | 10 | #REF! | 12 | #REF! | 11 | #REF! | REBUSAN | 5 Menit | [5 empty] | Mangkuk | 4 | [9 empty] | 4 |  |  | 4
1012006 | BIHUN SPECIAL GM BASO | 21 | BIHUN GMB | 9 |  | 0 | 10 | #REF! | 12 | #REF! | 11 | #REF! | REBUSAN | 5 Menit | [5 empty] | Mangkuk | 4 | [9 empty] | 4 |  |  | 4
1012007 | BIHUN SPECIAL GM PANGSIT | 24 | BIHUN GMP | 9 |  | 0 | 10 | #REF! | 12 | #REF! | 11 | #REF! | REBUSAN | 5 Menit | [5 empty] | Mangkuk | 4 | [9 empty] | 4 |  |  | 4
1012008 | BIHUN SPECIAL GM PNGST GR | 25 | BIHUN GMPG | 10 |  | 0 | 10 | #REF! | 12 | #REF! | 11 | #REF! | REBUSAN | 5 Menit | [5 empty] | Mangkuk | 4 | [9 empty] | 4 |  |  | 4
1012010 | BIHUN GORENG | 12 | BIHUN GR | 8 |  | 0 | 10 | #REF! | 12 | #REF! | 12 | #REF! | GORENGAN | 8 Menit | [5 empty] | Piring | 3 | [9 empty] | 3 |  |  | 3
1012011 | BIHUN GORENG SPECIAL | 20 | BIHUN GR SPC | 12 |  | 0 | 10 | #REF! | 12 | #REF! | 12 | #REF! | GORENGAN | 8 Menit |  |  |  | #REF! |  | Piring | 3 | [9 empty] | 3 |  |  | 3
1012012 | BIHUN MASAK | 11 | BIHUN MS | 8 |  | 0 | 10 | #REF! | 12 | #REF! | 12 | #REF! | GORENGAN | 8 Menit | [5 empty] | Mangkuk Besar | 2 | [9 empty] | 2 |  |  | 2
1012013 | BIHUN CAH JAMUR | 15 | BIHUN CJ | 8 |  | 0 | 10 | #REF! | 12 | #REF! | 12 | #REF! | GORENGAN | 8 Menit | [5 empty] | Piring | 3 | [9 empty] | 3 |  |  | 3
1012014 | BIHUN DAGING CAH CABAI | 22 | BIHUN DCB | 9 |  | 0 | 10 | #REF! | 12 | #REF! | 12 | #REF! | GORENGAN | 8 Menit | [5 empty] | Piring | 3 | [9 empty] | 3 |  |  | 3
1012015 | BIHUN CAP CAY | 13 | BIHUN CAP | 9 |  | 0 | 10 | #REF! | 12 | #REF! | 12 | #REF! | GORENGAN | 8 Menit | [5 empty] | Piring | 3 | [9 empty] | 3 |  |  | 3
1012016 | BIHUN AYAM CAH CABAI | 20 | BIHUN ACB | 9 |  | 0 | 10 | #REF! | 12 | #REF! | 12 | #REF! | GORENGAN | 8 Menit | [5 empty] | Piring | 3 | [9 empty] | 3 |  |  | 3
1012019 | BIHUN DOANK | 11 | BIHUN DOANK | 11 |  | 0 | 10 | #REF! | 12 | #REF! | 11 | #REF! | REBUSAN | 5 Menit |  |  |  | #REF! |  |  | 3 | [9 empty] | 3 |  |  | 3
1012021 | BIHUN BROKOLI SAPI LD HTM | 25 | BIHUN BSLH | 10 |  | 0 | 10 | #REF! | 12 | #REF! | 12 | #REF! | GORENGAN | 8 Menit | [6 empty] | 3 | [9 empty] | 3 |  |  | 3
1012022 | BIHUN AYAM LADA CHA CHA | 23 | BIHUN ALC | 9 |  | 0 | 10 | #REF! | 12 | #REF! | 11 | #REF! | REBUSAN | 5 Menit | [6 empty] | 3 | [9 empty] | 3 |  |  | 3
1014001 | NASI TIM | 8 | NASI TIM | 8 | N TIM | 5 | 10 | #REF! | 14 | #REF! | 11 | #REF! | REBUSAN | 5 Menit |  |  |  | cek |  | Piring | 2 | X | X | Delete | Delete | Delete | Delete | Delete | X | X | 2 | X | X | 2 | X | Delete | Delete | Tidak ke KDS
1014002 | NASI PUTIH | 10 | NASI | 4 | NASI | 4 | 10 | #REF! | 14 | #REF! | 12 | #REF! | REBUSAN | 5 Menit |  |  |  | cek |  | Piring | 3 | X | X | Delete | Delete | Delete | Delete | Delete | X | X | 3 | X | X | 3 | X | Delete | Delete | Tidak ke KDS
1014022 | NASI+ | 5 | NASI* | 5 | NASI* | 5 | 10 | [5 empty] | GORENGAN | 5 Menit | v |  |  |  |  | Piring | 3 | X | X | Delete | Delete | Delete | Delete | Delete | X | X | 3 | X | X | 3 | X | Delete | Delete | Tidak ke KDS
1014003 | NASI SPECIAL GM | 15 | NASI GM | 7 | N GM | 4 | 10 | #REF! | 14 | #REF! | 11 | #REF! | REBUSAN | 5 Menit |  |  |  | cek |  | Piring | 2 | X | X | Delete | Delete | Delete | Delete | Delete | X | X | 2 | X | X | 2 | X | Delete | Delete | Tidak ke KDS
1014004 | NASI GM BASO | 12 | NASI GMB | 8 | N GMB | 5 | 10 | #REF! | 14 | #REF! | 11 | #REF! | REBUSAN | 5 Menit |  |  |  | cek |  | Piring | 2 | X | X | Delete | Delete | Delete | Delete | Delete | X | X | 2 | X | X | 2 | X | Delete | Delete | Tidak ke KDS
1014005 | NASI GM PANGSIT | 15 | NASI GMP | 8 | N GMP | 5 | 10 | #REF! | 14 | #REF! | 11 | #REF! | REBUSAN | 5 Menit | [5 empty] | Piring | 2 | X | X | Delete | Delete | Delete | Delete | Delete | X | X | 2 | X | X | 2 | X | Delete | Delete | Tidak ke KDS
1014006 | NASI GM PNGST GR | 16 | NASI GMPG | 9 | N GMPG | 6 | 10 | #REF! | 14 | #REF! | 11 | #REF! | REBUSAN | 5 Menit | [5 empty] | Piring | 2 | X | X | Delete | Delete | Delete | Delete | Delete | X | X | 2 | X | X | 2 | X | Delete | Delete | Tidak ke KDS
1014008 | NASI DAGING CAH CABAI | 21 | NASI DCB | 8 | N DCB | 5 | 10 | #REF! | 14 | #REF! | 12 | #REF! | GORENGAN | 8 Menit | [5 empty] | Piring | 3 | X | X | Delete | Delete | Delete | Delete | Delete | X | X | 3 | X | X | 3 | X | Delete | Delete | Tidak ke KDS
1014009 | NASI CAP CAY | 12 | NASI CAP | 8 | N CAP | 5 | 10 | #REF! | 14 | #REF! | 12 | #REF! | GORENGAN | 8 Menit | [5 empty] | Piring | 3 | X | X | Delete | Delete | Delete | Delete | Delete | X | X | 3 | X | X | 3 | X | Delete | Delete | Tidak ke KDS
1014010 | NASI AYAM CAH CABAI | 19 | NASI ACB | 8 | N ACB | 5 | 10 | #REF! | 14 | #REF! | 12 | #REF! | GORENGAN | 8 Menit | [5 empty] | Piring | 3 | X | X | Delete | Delete | Delete | Delete | Delete | X | X | 3 | X | X | 3 | X | Delete | Delete | Tidak ke KDS
1014011 | NASI GORENG | 11 | NASI GR | 7 | NG | 2 | 10 | #REF! | 14 | #REF! | 12 | #REF! | GORENGAN | 8 Menit |  | NASI GR |  |  |  | Piring | 3 | X | X | Delete | Delete | Delete | Delete | Delete | X | X | 3 | X | X | 3 | X | Delete | Delete | Tidak ke KDS
1014012 | NASI GORENG SPECIAL | 19 | NASI GR SPC | 11 | NG+ | 3 | 10 | #REF! | 14 | #REF! | 12 | #REF! | GORENGAN | 8 Menit |  | NASI GR |  | #REF! |  | Piring | 3 | X | X | Delete | Delete | Delete | Delete | Delete | X | X | 3 | X | X | 3 | X | Delete | Delete | Tidak ke KDS
1014013 | NASI CAH JAMUR | 14 | NASI CJ | 7 | N CJ | 4 | 10 | #REF! | 14 | #REF! | 12 | #REF! | GORENGAN | 8 Menit | [5 empty] | Piring | 3 | X | X | Delete | Delete | Delete | Delete | Delete | X | X | 3 | X | X | 3 | X | Delete | Delete | Tidak ke KDS
1014017 | NASI BROKOLI SAPI LD HTM | 24 | NASI BSLH | 9 | N BSLH | 6 | 10 | #REF! | 14 | #REF! | 12 | #REF! | GORENGAN | 8 Menit | [5 empty] | Piring | 3 | X | X | Delete | Delete | Delete | Delete | Delete | X | X | 3 | X | X | 3 | X | Delete | Delete | Tidak ke KDS
1014018 | NASI GORENG REGULER | 19 | NASI GSC RG | 11 | NGSC R | 6 | 10 | #REF! | 14 | #REF! | 12 | #REF! | GORENGAN | 8 Menit |  | NGSC RG | Grouping NGSC Reguler/ Small | #REF! |  | Piring | 3 | X | X | Delete | Delete | Delete | Delete | Delete | X | X | 3 | X | X | 3 | X | Delete | Delete | Tidak ke KDS
1014019 | NASI GORENG SMKD CHICKEN | 24 | NASI GSC SM | 11 | NGSC S | 6 | 10 | #REF! | 14 | #REF! | 12 | #REF! | GORENGAN | 8 Menit |  | NGSC SM |  | #REF! |  | Piring | 3 | X | X | Delete | Delete | Delete | Delete | Delete | X | X | 3 | X | X | 3 | X | Delete | Delete | Tidak ke KDS
1014023 | NASI GORENG REGULER SPC | 23 | NASI GSC RG SPC | 15 | NGSC R+ | 7 | 10 | [5 empty] | GORENGAN | 8 Menit |  | NGSC RG |  |  |  | Piring | 3 | X | X | Delete | Delete | Delete | Delete | Delete | X | X | 3 | X | X | 3 | X | Delete | Delete | Tidak ke KDS
1014024 | NASI GORENG SMKD CHICKEN SPC | 28 | NASI GSC SM SPC | 15 | NGSC S+ | 7 | 10 | [5 empty] | GORENGAN | 8 Menit |  | NGSC SM |  |  |  | Piring | 3 | X | X | Delete | Delete | Delete | Delete | Delete | X | X | 3 | X | X | 3 | X | Delete | Delete | Tidak ke KDS
1014020 | NASI AYAM LADA CHA CHA | 22 | NASI ALC | 8 | N ALC | 5 | 10 | #REF! | 14 | #REF! | 11 | #REF! | REBUSAN | 5 Menit | [5 empty] | Piring | 3 | X | X | Delete | Delete | Delete | Delete | Delete | X | X | 3 | X | X | 3 | X | Delete | Delete | Tidak ke KDS
1014021 | NASI AYAM THAI | 14 | NASI AT | 7 | N AT | 4 | 10 | #REF! | 14 | #REF! | 12 | #REF! | GORENGAN | 8 Menit | [5 empty] | Piring | 3 | X | X | Delete | Delete | Delete | Delete | Delete | X | X | 3 | X | X | 3 | X | Delete | Delete | Tidak ke KDS
1015001 | AYAM GORENG | 11 | AYAM G | 6 | AGR | 3 | 10 | #REF! | 15 | #REF! | 12 | #REF! | GORENGAN | 8 Menit | [5 empty] | Piring | 3 | X | X | Delete | Delete | Delete | Delete | Delete | X | X | 3 | X | X | 3 | X | Delete | Delete | Tidak ke KDS
1015003 | AYAM CAH CABAI | 14 | AYAM CB | 7 | ACB | 3 | 10 | #REF! | 15 | #REF! | 12 | #REF! | GORENGAN | 8 Menit | [5 empty] | Piring | 3 | X | X | Delete | Delete | Delete | Delete | Delete | X | X | 3 | X | X | 3 | X | Delete | Delete | Tidak ke KDS
1015004 | AYAM CAH JAMUR | 14 | AYAM CJ | 7 | ACJ | 3 | 10 | #REF! | 15 | #REF! | 12 | #REF! | GORENGAN | 8 Menit | [5 empty] | Piring | 3 | X | X | Delete | Delete | Delete | Delete | Delete | X | X | 3 | X | X | 3 | X | Delete | Delete | Tidak ke KDS
1015005 | DAGING CAH CABAI | 16 | DAGING CB | 9 | DCB | 3 | 10 | #REF! | 15 | #REF! | 12 | #REF! | GORENGAN | 8 Menit | [5 empty] | Piring | 3 | X | X | Delete | Delete | Delete | Delete | Delete | X | X | 3 | X | X | 3 | X | Delete | Delete | Tidak ke KDS
1015006 | CAP CAY | 7 | CAP | 3 | CAP | 3 | 10 | #REF! | 15 | #REF! | 12 | #REF! | GORENGAN | 8 Menit | [5 empty] | Piring | 3 | X | X | Delete | Delete | Delete | Delete | Delete | X | X | 3 | X | X | 3 | X | Delete | Delete | Tidak ke KDS
1015007 | CAP CAY KUAH | 12 | CAP KUAH | 8 | CAP K | 5 | 10 | #REF! | 15 | #REF! | 12 | #REF! | GORENGAN | 8 Menit | [5 empty] | Mangkuk | 4 | X | X | Delete | Delete | Delete | Delete | Delete | X | X | 4 | X | X | 4 | X | Delete | Delete | Tidak ke KDS
1015008 | FU YUNG HAY | 11 | F Y H | 5 | FYH | 3 | 10 | #REF! | 15 | #REF! | 12 | #REF! |  | 8 Menit | [6 empty] | 3 | X | X | Delete | Delete | Delete | Delete | Delete | X | X | 3 | X | X | 3 | X | Delete | Delete | Tidak ke KDS
1015012 | BROKOLI SAPI LD HTM | 19 | BROKOLI SLH | 11 | BSLH | 4 | 10 | #REF! | 15 | #REF! | 12 | #REF! | GORENGAN | 8 Menit |  |  |  | #REF! |  | Piring | 3 | X | X | Delete | Delete | Delete | Delete | Delete | X | X | 3 | X | X | 3 | X | Delete | Delete | Tidak ke KDS
1015013 | AYAM GORENG SAUS THAI | 21 | AYAM GR ST | 10 | AT | 2 | 10 | #REF! | 15 | #REF! | 12 | #REF! | GORENGAN | 8 Menit | [5 empty] | Piring | 3 | X | X | Delete | Delete | Delete | Delete | Delete | X | X | 3 | X | X | 3 | X | Delete | Delete | Tidak ke KDS
1015014 | BROKOLI SAUS TIRAM | 18 | Brokoli ST-S | 12 | BST-S | 5 | 10 | #REF! | 15 | #REF! | 12 | #REF! | REBUSAN | 5 Menit |  |  |  | #REF! |  | Piring Side Dish | 4 | X | X | Delete | Delete | Delete | Delete | Delete | X | X | 4 | X | X | 4 | X | Delete | Delete | Tidak ke KDS
1015015 | CAISIM SAUS TIRAM | 17 | Caisim ST-S | 11 | CST-S | 5 | 10 | #REF! | 15 | #REF! | 12 | #REF! | REBUSAN | 5 Menit |  |  |  | #REF! |  | Piring Side Dish | 4 | X | X | Delete | Delete | Delete | Delete | Delete | X | X | 4 | X | X | 4 | X | Delete | Delete | Tidak ke KDS
1015016 | TAOGE SAUS TIRAM | 16 | Taoge ST-S | 10 | TST-S | 5 | 10 | #REF! | 15 | #REF! | 12 | #REF! | REBUSAN | 5 Menit | [5 empty] | Piring Side Dish | 4 | X | X | Delete | Delete | Delete | Delete | Delete | X | X | 4 | X | X | 4 | X | Delete | Delete | Tidak ke KDS
1015017 | BROKOLI SAUS TIRAM | 18 | Brokoli ST-R | 12 | BST-R | 5 | 10 | #REF! | 15 | #REF! | 12 | #REF! | REBUSAN | 5 Menit |  |  |  | #REF! |  | Piring Side Dish | 4 | X | X | Delete | Delete | Delete | Delete | Delete | X | X | 4 | X | X | 4 | X | Delete | Delete | Tidak ke KDS
1015018 | CAISIM SAUS TIRAM | 17 | Caisim ST-R | 11 | CST-R | 5 | 10 | #REF! | 15 | #REF! | 12 | #REF! | REBUSAN | 5 Menit |  |  |  | #REF! |  | Piring Side Dish | 4 | X | X | Delete | Delete | Delete | Delete | Delete | X | X | 4 | X | X | 4 | X | Delete | Delete | Tidak ke KDS
1015019 | TAOGE SAUS TIRAM | 16 | Taoge ST-R | 10 | TST-R | 5 | 10 | #REF! | 15 | #REF! | 12 | #REF! | REBUSAN | 5 Menit | [5 empty] | Piring Side Dish | 4 | X | X | Delete | Delete | Delete | Delete | Delete | X | X | 4 | X | X | 4 | X | Delete | Delete | Tidak ke KDS
1016001 | 1/2 BAKSO KUAH | 14 | 1/2 BAKSO K | 11 | 1/2 BK | 6 | 10 | #REF! | 16 | #REF! | 11 | #REF! | REBUSAN | 5 Menit |  |  |  | #REF! |  | Mangkuk | 4 | X | X | Delete | Delete | Delete | Delete | Delete | X | X | 4 | X | X | 4 | X | Delete | Delete | Tidak ke KDS
1016003 | 1/2 PANGSIT KUAH | 16 | 1/2 PANGS K | 11 | 1/2 PK | 6 | 10 | #REF! | 16 | #REF! | 11 | #REF! | REBUSAN | 5 Menit |  |  |  | #REF! |  | Mangkuk | 4 | X | X | Delete | Delete | Delete | Delete | Delete | X | X | 4 | X | X | 4 | X | Delete | Delete | Tidak ke KDS
1016005 | 1/2 PANGSIT GORENG | 18 | 1/2 PANGS GR | 12 | 1/2 PG | 6 | 10 | #REF! | 16 | #REF! | 12 | #REF! | GORENGAN | 5 Menit | v |  |  | #REF! |  | Piring | 3 | X | X | Delete | Delete | Delete | Delete | Delete | X | X | 3 | X | X | 3 | X | Delete | Delete | Tidak ke KDS
1016006 | PANGSIT GORENG | 14 | PANGS GR | 8 | PG | 2 | 10 | #REF! | 16 | #REF! | 12 | #REF! | GORENGAN | 5 Menit | v |  |  |  |  | Piring | 3 | X | X | Delete | Delete | Delete | Delete | Delete | X | X | 3 | X | X | 3 | X | Delete | Delete | Tidak ke KDS
1016007 | 1/2 TAHU BASO | 13 | 1/2 TAHU B | 10 | 1/2 TB | 6 | 10 | #REF! | 16 | #REF! | 11 | #REF! | REBUSAN | 5 Menit | [5 empty] | Mangkuk | 4 | X | X | Delete | Delete | Delete | Delete | Delete | X | X | 4 | X | X | 4 | X | Delete | Delete | Tidak ke KDS
1016008 | TAHU BASO | 9 | TAHU BS | 7 | TB | 2 | 10 | #REF! | 16 | #REF! | 11 | #REF! |  | 5 Menit | [6 empty] | 3 | X | X | Delete | Delete | Delete | Delete | Delete | X | X | 3 | X | X | 3 | X | Delete | Delete | Tidak ke KDS
1016010 | SIOMAY | 6 | SIOMAY | 6 | SIO | 3 | 10 | #REF! | 16 | #REF! | 11 | #REF! |  | 5 Menit | [6 empty] | 3 | X | X | Delete | Delete | Delete | Delete | Delete | X | X | 3 | X | X | 3 | X | Delete | Delete | Tidak ke KDS
1016011 | SIOMAY GORENG | 13 | SIOMAY G | 8 | SIO | 3 | 10 | #REF! | 16 | #REF! | 12 | #REF! |  | 8 Menit | [6 empty] | 3 | X | X | Delete | Delete | Delete | Delete | Delete | X | X | 3 | X | X | 3 | X | Delete | Delete | Tidak ke KDS
1016012 | TELUR MATA SAPI | 15 | TELUR MS | 8 | TLR MS | 6 | 10 | #REF! | 16 | #REF! | 12 | #REF! |  | 8 Menit | [6 empty] | 3 | X | X | Delete | Delete | Delete | Delete | Delete | X | X | 3 | X | X | 3 | X | Delete | Delete | Tidak ke KDS
1016014 | BAKSO CAMPUR KOMPLIT | 20 | BAKSO CMPK | 10 | BS CPK | 6 | 10 | #REF! | 16 | #REF! | 11 | #REF! | REBUSAN | 5 Menit | [5 empty] | Mangkuk | 4 | X | X | Delete | Delete | Delete | Delete | Delete | X | X | 4 | X | X | 4 | X | Delete | Delete | Tidak ke KDS
1016015 | 2 PCS PANGSIT GORENG | 20 | 2 PCS PG | 8 | 2PC PG | 6 | 10 | #REF! | 16 | #REF! | 12 | #REF! |  | 8 Menit | [6 empty] | 3 | X | X | Delete | Delete | Delete | Delete | Delete | X | X | 3 | X | X | 3 | X | Delete | Delete | Tidak ke KDS
1016016 | LUMPIA SAUS THAI | 16 | LUMPIA ST | 9 | LST | 3 | 10 | #REF! | 16 | #REF! | 12 | #REF! |  | 8 Menit | [6 empty] | 3 | X | X | Delete | Delete | Delete | Delete | Delete | X | X | 3 | X | X | 3 | X | Delete | Delete | Tidak ke KDS
1016017 | KERUPUK | 7 | KRPK | 4 | KRPK | 4 | 10 | #REF! | 16 | #REF! | 12 | #REF! |  | 8 Menit | [6 empty] | 3 | X | X | Delete | Delete | Delete | Delete | Delete | X | X | 3 | X | X | 3 | X | Delete | Delete | Tidak ke KDS
1016018 | SPICY MAYO SEAFOOD BALL | 23 | SPICY MAYO SB | 13 | S MAYO | 6 | 10 | #REF! | 16 | #REF! | 12 | #REF! | GORENGAN | 8 Menit |  |  |  | #REF! |  | Piring Side Dish | 4 | X | X | Delete | Delete | Delete | Delete | Delete | X | X | 4 | X | X | 4 | X | Delete | Delete | Tidak ke KDS
1016019 | SIOMAY 2 | 8 | SIOMAY 2 | 8 | SIO 2 | 5 | 10 | #REF! | 16 | #REF! | 11 | #REF! | REBUSAN | 5 Menit | [5 empty] | Piring Side Dish | 4 | X | X | Delete | Delete | Delete | Delete | Delete | X | X | 4 | X | X | 4 | X | Delete | Delete | Tidak ke KDS
1016020 | SIOMAY 4 | 8 | SIOMAY 4 | 8 | SIO 4 | 5 | 10 | #REF! | 16 | #REF! | 11 | #REF! | REBUSAN | 5 Menit | [5 empty] | Piring Side Dish | 4 | X | X | Delete | Delete | Delete | Delete | Delete | X | X | 4 | X | X | 4 | X | Delete | Delete | Tidak ke KDS
1016021 | SIOMAY 2 GORENG | 15 | SIOMAY 2G | 9 | SIO 2G | 6 | 10 | #REF! | 16 | #REF! | 12 | #REF! | GORENGAN | 8 Menit | [5 empty] | Piring Side Dish | 4 | X | X | Delete | Delete | Delete | Delete | Delete | X | X | 4 | X | X | 4 | X | Delete | Delete | Tidak ke KDS
1016022 | SIOMAY 4 GORENG | 15 | SIOMAY 4G | 9 | SIO 4G | 6 | 10 | #REF! | 16 | #REF! | 12 | #REF! | GORENGAN | 8 Menit | [5 empty] | Piring Side Dish | 4 | X | X | Delete | Delete | Delete | Delete | Delete | X | X | 4 | X | X | 4 | X | Delete | Delete | Tidak ke KDS
1016503 | SAYUR KUAH | 10 | SAYUR K | 7 | SYR K | 5 | 10 | #REF! | 16 | #REF! | 11 | #REF! | REBUSAN | 5 Menit | [5 empty] | Mangkuk | 4 | X | X | Delete | Delete | Delete | Delete | Delete | X | X | 4 | X | X | 4 | X | Delete | Delete | Tidak ke KDS
1019001 | BAKMI AYAM (K) | 14 | BAKMI A (K) | 11 | B A | 3 | 10 | [5 empty] | REBUSAN | 5 Menit | [5 empty] | Mangkuk | 4 | X | X | Delete | Delete | Delete | Delete | Delete | X | X | 3 | X | X | 3 | X | Delete | Delete | Tidak ke KDS
1019002 | BAKMI GORENG (K) | 16 | BAKMI GR (K) |  | BG | 2 | [6 empty] | GORENGAN | 8 Menit |  | BAKMI GRG |  |  |  | Piring | 3
1019003 | AYAM CAH CABAI (K) |  | AYAM CB (K) |  | ACB | 3 | [6 empty] | GORENGAN | 8 Menit | [5 empty] | Piring | 3
1019004 | NASI PUTIH (K) | 14 | NASI (K) | 8 | NASI | 4 | 10 | #REF! | 71 | #REF! | 12 | #REF! | REBUSAN | 5 Menit | [5 empty] | Piring | 3 | X | X | Delete | Delete | Delete | Delete | Delete | X | X | 4 | X | X | 4 | X | Delete | Delete | Tidak ke KDS
3021001 | FRUIT PUNCH | 11 | FRUIT P | 7 | #REF! | #REF! | 20 | #REF! | 21 | #REF! | 21 | #REF! | REBUSAN
3021003 | LEMON ES TEA | 12 | LEMON ST | 8 |  | 0 | 20 | #REF! | 21 | #REF! | 21 | #REF! | REBUSAN
3021004 | ES JERUK | 8 | ES JERUK | 8 |  | 0 | 20 | #REF! | 21 | #REF! | 21 | #REF! | REBUSAN
3021005 | AIR JERUK | 9 | AIR JERUK | 9 |  | 0 | 20 | #REF! | 21 | #REF! | 21 | #REF! | REBUSAN
3021006 | JERUK POLOS | 11 | JERUK PLS | 9 |  | 0 | 20 | #REF! | 21 | #REF! | 21 | #REF! | REBUSAN
3021007 | SODA SUSU | 9 | SODA SUSU | 9 |  | 0 | 20 | #REF! | 21 | #REF! | 21 | #REF! | REBUSAN
3021008 | FRESH LIME ES | 13 | F LIME S | 8 |  | 0 | 20 | #REF! | 21 | #REF! | 21 | #REF! | REBUSAN
3021009 | AQUA 330 ML | 11 | AQUA | 4 |  | 0 | 20 | #REF! | 21 | #REF! | 21 | #REF! | REBUSAN
3021020 | TEH KOTAK | 9 | TEH KOTAK | 9 |  | 0 | 20 | #REF! | 21 | #REF! | 21 | #REF! | REBUSAN
3021021 | ES TEH | 6 | ES TEH | 6 |  | 0 | 20 | #REF! | 21 | #REF! | 21 | #REF! | REBUSAN
3021022 | ES TEH MANIS | 12 | ES TEH MNS | 10 |  | 0 | 20 | #REF! | 21 | #REF! | 21 | #REF! | REBUSAN
3021023 | TEH CELUP | 9 | TEH CLP | 7 |  | 0 | 20 | #REF! | 21 | #REF! | 21 | #REF! | REBUSAN
3021024 | TEH CELUP MANIS | 15 | TEH CLP MNS | 11 |  | 0 | 20 | #REF! | 21 | #REF! | 21 | #REF! | REBUSAN
3021025 | TEH | 3 | TEH | 3 |  | 0 | 20 | #REF! | 21 | #REF! | 21 | #REF! | REBUSAN
3021026 | TEH MANIS | 9 | TEH MNS | 7 |  | 0 | 20 | #REF! | 21 | #REF! | 21 | #REF! | REBUSAN
3021027 | AIR SODA | 8 | AIR SODA | 8 |  | 0 | 20 | #REF! | 21 | #REF! | 21 | #REF! | REBUSAN
3021028 | JERUK NIPIS | 11 | JERUK NIPIS | 11 |  | 0 | 20 | #REF! | 21 | #REF! | 21 | #REF! | REBUSAN
3021029 | SUSU | 4 | SUSU | 4 |  | 0 | 20 | #REF! | 21 | #REF! | 21 | #REF! | REBUSAN
3021030 | LEMON BLUSH | 11 | LEMON BLUSH | 11 |  | 0 | 20 | #REF! | 21 | #REF! | 21 | #REF! | REBUSAN
3021031 | GREEN TEA | 9 | GREEN TEA | 9 |  | 0 | 20 | #REF! | 21 | #REF! | 21 | #REF! | REBUSAN
3021032 | ES GREEN TEA | 12 | ES GT | 5 |  | 0 | 20 | #REF! | 21 | #REF! | 21 | #REF! | REBUSAN
3021033 | HOT GREEN TEA | 13 | HOT GT | 6 |  | 0 | 20 | #REF! | 21 | #REF! | 21 | #REF! | REBUSAN
3021034 | ICED COFFEE JELLY | 17 | ICED CJ | 7 |  | 0 | 20 | #REF! | 21 | #REF! | 21 | #REF! | REBUSAN
3021035 | PINEAPPLE COOLER | 16 | PINEAPPLE. C. | 13 |  | 0 | 20 | #REF! | 21 | #REF! | 21 | #REF! | REBUSAN
3021039 | MANGO PEACH P | 13 | MANGO PEACH P | 13 |  | 0 | 20 | #REF! | 21 | #REF! | 21 | #REF! | REBUSAN
3021040 | KOPI PANAS | 10 | KOPI PNS | 8 |  | 0 | 20 | #REF! | 21 | #REF! | 21 | #REF! | REBUSAN
3021041 | CP TEA | 6 | CP TEA | 6 |  | 0 | 20 | #REF! | 21 | #REF! | 21 | #REF! | REBUSAN
3021043 | LYCHEE ES THE | 13 | LYCHEE ST | 9 |  | 0 | 20 | #REF! | 21 | #REF! | 21 | #REF! | REBUSAN
3021044 | AQUA 600 ML | 11 | AQUA * | 6 |  | 0 | 20 | #REF! | 21 | #REF! | 21 | #REF! | REBUSAN
3021045 | BOLA UBI JELLY | 14 | BOLA UJ | 7 |  | 0 | 20 | #REF! | 21 | #REF! | 21 | #REF! | REBUSAN
3022001 | JUICE STRBERRY | 14 | JC STRBERRY | 11 |  | 0 | 20 | #REF! | 22 | #REF! | 21 | #REF! | REBUSAN
3022002 | JUICE KOPYOR | 12 | JC KOPYOR | 9 |  | 0 | 20 | #REF! | 22 | #REF! | 21 | #REF! | REBUSAN
3022003 | JUICE MELON | 11 | JC MELON | 8 |  | 0 | 20 | #REF! | 22 | #REF! | 21 | #REF! | REBUSAN
3022004 | JUICE MANGGA | 12 | JC MANGGA | 9 |  | 0 | 20 | #REF! | 22 | #REF! | 21 | #REF! | REBUSAN
3022005 | JUICE ALPOKAT | 13 | JC ALPOKAT | 10 |  | 0 | 20 | #REF! | 22 | #REF! | 21 | #REF! | REBUSAN
3022006 | JUICE SEMANGKA | 14 | JC SEMANGKA | 11 |  | 0 | 20 | #REF! | 22 | #REF! | 21 | #REF! | REBUSAN
3022007 | JUICE JAMBU | 11 | JC JAMBU | 8 |  | 0 | 20 | #REF! | 22 | #REF! | 21 | #REF! | REBUSAN
3022008 | JUICE TOMAT | 11 | JC TOMAT | 8 |  | 0 | 20 | #REF! | 22 | #REF! | 21 | #REF! | REBUSAN
3022009 | JUICE PEPAYA | 12 | JC PEPAYA | 9 |  | 0 | 20 | #REF! | 22 | #REF! | 21 | #REF! | REBUSAN
3022010 | JUICE NANAS | 11 | JC NANAS | 8 |  | 0 | 20 | #REF! | 22 | #REF! | 21 | #REF! | REBUSAN
3022011 | JUICE SIRSAK | 12 | JC SIRSAK | 9 |  | 0 | 20 | #REF! | 22 | #REF! | 21 | #REF! | REBUSAN
3022101 | JUICE MIX | 9 | JC MIX | 6 |  | 0 | 20 | #REF! | 22 | #REF! | 21 | #REF! | REBUSAN
3023001 | BUAH SEGAR | 10 | BUAH SEGAR | 10 |  | 0 | 20 | #REF! | 23 | #REF! | 21 | #REF! | REBUSAN
3023002 | RUJAK | 5 | RUJAK | 5 |  | 0 | 20 | #REF! | 23 | #REF! | 21 | #REF! | REBUSAN
3024001 | ICE CREAM CHOCO | 15 | IC CHOCO | 8 |  | 0 | 20 | #REF! | 24 | #REF! | 21 | #REF! | REBUSAN
3024002 | ICE CREAM MOCCA | 15 | IC MOCCA | 8 |  | 0 | 20 | #REF! | 24 | #REF! | 21 | #REF! | REBUSAN
3024003 | ICE CREAM NEO | 13 | IC NEO | 6 |  | 0 | 20 | #REF! | 24 | #REF! | 21 | #REF! | REBUSAN
3024004 | ICE CREAM OGURA | 15 | IC OGURA | 8 |  | 0 | 20 | #REF! | 24 | #REF! | 21 | #REF! | REBUSAN
3024005 | ICE CREAM TUTTI | 15 | IC TUTTI | 8 |  | 0 | 20 | #REF! | 24 | #REF! | 21 | #REF! | REBUSAN
3024006 | ICE CREAM VANILA | 16 | IC VANILA | 9 |  | 0 | 20 | #REF! | 24 | #REF! | 21 | #REF! | REBUSAN
7071022 | BGM JUNIOR | 10 | BGM Jr | 6 | BGM Jr | 6 | 70 | #REF! | 71 | #REF! | 11 | #REF! | REBUSAN | 5 Menit | [6 empty] | X | X | X | Delete | Delete | Delete | Delete | Delete | X | X | X | X | X | X | X | Delete | Delete | Tidak ke KDS
7071023 | BGM JUNIOR + AQUA 330 ML | 24 | BGM Jr+AQUA | 11 | BGM Jr+AQ | 9 | 70 | #REF! | 71 | #REF! | 11 | #REF! | REBUSAN | 5 Menit |  |  |  | #REF! |  |  | X | X | X | Delete | Delete | Delete | Delete | Delete | X | X | X | X | X | X | X | Delete | Delete | Tidak ke KDS
7071024 | BGM JUNIOR + SOSRO | 18 | BGM Jr+SOSRO | 12 | BGM Jr+SO | 9 | 70 | #REF! | 71 | #REF! | 11 | #REF! | REBUSAN | 5 Menit |  |  |  | #REF! |  |  | X | X | X | Delete | Delete | Delete | Delete | Delete | X | X | X | X | X | X | X | Delete | Delete | Tidak ke KDS
7071025 | BGM JUNIOR + FRUIT PUNCH | 24 | BGM Jr+FP | 9 |  | 0 | 70 | #REF! | 71 | #REF! | 11 | #REF! |  | 5 Menit | [6 empty] | X | X | X | Delete | Delete | Delete | Delete | Delete | X | X | X | X | X | X | X | Delete | Delete | Tidak ke KDS
7071026 | BGMP JUNIOR | 11 | BGMP Jr | 7 | BGMP Jr | 7 | 70 | #REF! | 71 | #REF! | 11 | #REF! | REBUSAN | 5 Menit | [6 empty] | X | X | X | Delete | Delete | Delete | Delete | Delete | X | X | X | X | X | X | X | Delete | Delete | Tidak ke KDS
7071027 | BGMP JUNIOR + AQUA 330 ML | 25 | BGMP Jr+AQUA | 12 | BGMP Jr+AQ | 10 | 70 | #REF! | 71 | #REF! | 11 | #REF! | REBUSAN | 5 Menit |  |  |  | #REF! |  |  | X | X | X | Delete | Delete | Delete | Delete | Delete | X | X | X | X | X | X | X | Delete | Delete | Tidak ke KDS
7071028 | BGMP JUNIOR + SOSRO | 19 | BGMP Jr+SOSRO | 13 | BGMP Jr+SO | 10 | 70 | #REF! | 71 | #REF! | 11 | #REF! | REBUSAN | 5 Menit |  |  |  | #REF! |  |  | X | X | X | Delete | Delete | Delete | Delete | Delete | X | X | X | X | X | X | X | Delete | Delete | Tidak ke KDS
7071029 | BGMP JUNIOR + FRUIT PUNCH | 25 | BGMP Jr+FP | 10 |  | 0 | 70 | #REF! | 71 | #REF! | 11 | #REF! |  | 5 Menit | [6 empty] | X | X | X | Delete | Delete | Delete | Delete | Delete | X | X | X | X | X | X | X | Delete | Delete | Tidak ke KDS
7071030 | BGr JUNIOR | 10 | BGr Jr | 6 | BGR Jr | 6 | 70 | #REF! | 71 | #REF! | 12 | #REF! | GORENGAN | 8 Menit | [6 empty] | X | X | X | Delete | Delete | Delete | Delete | Delete | X | X | X | X | X | X | X | Delete | Delete | Tidak ke KDS
7071031 | BGr JUNIOR + AQUA 330 ML | 24 | BGr Jr+AQUA | 11 | BG Jr+AQ | 8 | 70 | #REF! | 71 | #REF! | 12 | #REF! | GORENGAN | 8 Menit |  |  |  | #REF! |  |  | X | X | X | Delete | Delete | Delete | Delete | Delete | X | X | X | X | X | X | X | Delete | Delete | Tidak ke KDS
7071032 | BGr JUNIOR + SOSRO | 18 | BGr Jr+SOSRO | 12 | BG Jr+SO | 8 | 70 | #REF! | 71 | #REF! | 12 | #REF! | GORENGAN | 8 Menit |  |  |  | #REF! |  |  | X | X | X | Delete | Delete | Delete | Delete | Delete | X | X | X | X | X | X | X | Delete | Delete | Tidak ke KDS
7071033 | BGr JUNIOR + FRUIT PUNCH | 24 | BGr Jr+FP | 9 |  | 0 | 70 | #REF! | 71 | #REF! | 12 | #REF! |  | 8 Menit | [6 empty] | X | X | X | Delete | Delete | Delete | Delete | Delete | X | X | X | X | X | X | X | Delete | Delete | Tidak ke KDS
7071034 | BGMB JUNIOR | 11 | BGMB Jr | 7 | BGMB Jr | 7 | 70 | #REF! | 71 | #REF! | 11 | #REF! | REBUSAN | 5 Menit | [6 empty] | X | X | X | Delete | Delete | Delete | Delete | Delete | X | X | X | X | X | X | X | Delete | Delete | Tidak ke KDS
7071035 | BGMB JUNIOR + AQUA 330 ML | 25 | BGMB Jr+AQUA | 12 | BGMB Jr+AQ | 10 | 70 | #REF! | 71 | #REF! | 11 | #REF! | REBUSAN | 5 Menit |  |  |  | #REF! |  |  | X | X | X | Delete | Delete | Delete | Delete | Delete | X | X | X | X | X | X | X | Delete | Delete | Tidak ke KDS
7071036 | BGMB JUNIOR + SOSRO | 19 | BGMB Jr+SOSRO | 13 | BGMB Jr+SO | 10 | 70 | #REF! | 71 | #REF! | 11 | #REF! | REBUSAN | 5 Menit |  |  |  | #REF! |  |  | X | X | X | Delete | Delete | Delete | Delete | Delete | X | X | X | X | X | X | X | Delete | Delete | Tidak ke KDS
7071037 | BGMB JUNIOR + FRUIT PUNCH | 25 | BGMB Jr+FP | 10 |  | 0 | 70 | #REF! | 71 | #REF! | 11 | #REF! |  | 5 Menit | [6 empty] | X | X | X | Delete | Delete | Delete | Delete | Delete | X | X | X | X | X | X | X | Delete | Delete | Tidak ke KDS
7071038 | NGM JUNIOR | 10 | NGM Jr | 6 | NGM Jr | 6 | 70 | #REF! | 71 | #REF! | 11 | #REF! | REBUSAN | 5 Menit | [6 empty] | X | X | X | Delete | Delete | Delete | Delete | Delete | X | X | X | X | X | X | X | Delete | Delete | Tidak ke KDS
7071039 | NGM JUNIOR + AQUA 330 ML | 24 | NGM Jr+AQUA | 11 | NGM Jr+AQ | 9 | 70 | #REF! | 71 | #REF! | 11 | #REF! | REBUSAN | 5 Menit |  |  |  | #REF! |  |  | X | X | X | Delete | Delete | Delete | Delete | Delete | X | X | X | X | X | X | X | Delete | Delete | Tidak ke KDS
7071040 | NGM JUNIOR + SOSRO | 18 | NGM Jr+SOSRO | 12 | NGM Jr+SO | 9 | 70 | #REF! | 71 | #REF! | 11 | #REF! | REBUSAN | 5 Menit |  |  |  | #REF! |  |  | X | X | X | Delete | Delete | Delete | Delete | Delete | X | X | X | X | X | X | X | Delete | Delete | Tidak ke KDS
7071041 | NGM JUNIOR + FRUIT PUNCH | 24 | NGM Jr+FP | 9 |  | 0 | 70 | #REF! | 71 | #REF! | 11 | #REF! |  | 5 Menit | [6 empty] | X | X | X | Delete | Delete | Delete | Delete | Delete | X | X | X | X | X | X | X | Delete | Delete | Tidak ke KDS
7071042 | NGSC SMALL | 10 | NGSC S | 6 |  | 0 | 70 | #REF! | 71 | #REF! | 12 | #REF! |  | 8 Menit | [6 empty] | X | X | X | Delete | Delete | Delete | Delete | Delete | X | X | X | X | X | X | X | Delete | Delete | Tidak ke KDS
7071043 | NGSC SMALL + AQUA 330 ML | 24 | NGSC S+AQUA | 11 | NGSC S+AQ | 9 | 70 | #REF! | 71 | #REF! | 12 | #REF! |  | 8 Menit |  |  |  | #REF! |  |  | X | X | X | Delete | Delete | Delete | Delete | Delete | X | X | X | X | X | X | X | Delete | Delete | Tidak ke KDS
7071044 | NGSC SMALL + SOSRO | 18 | NGSC S+SOSRO | 12 | NGSC S+TS | 9 | 70 | #REF! | 71 | #REF! | 12 | #REF! |  | 8 Menit |  |  |  | #REF! |  |  | X | X | X | Delete | Delete | Delete | Delete | Delete | X | X | X | X | X | X | X | Delete | Delete | Tidak ke KDS
7071045 | NGSC SMALL + FRUIT PUNCH | 24 | NGSC S+FP | 9 |  | 0 | 70 | #REF! | 71 | #REF! | 12 | #REF! |  | 8 Menit | [6 empty] | X | X | X | Delete | Delete | Delete | Delete | Delete | X | X | X | X | X | X | X | Delete | Delete | Tidak ke KDS
7071046 | NGMP JUNIOR | 11 | NGMP Jr | 7 | NGMP Jr | 7 | 70 | #REF! | 71 | #REF! | 11 | #REF! |  | 5 Menit | [6 empty] | X | X | X | Delete | Delete | Delete | Delete | Delete | X | X | X | X | X | X | X | Delete | Delete | Tidak ke KDS
7071047 | NGMP JUNIOR + AQUA 330 ML | 25 | NGMP Jr+AQUA | 12 | NGMP Jr+Aq | 10 | 70 | #REF! | 71 | #REF! | 11 | #REF! |  | 5 Menit |  |  |  | #REF! |  |  | X | X | X | Delete | Delete | Delete | Delete | Delete | X | X | X | X | X | X | X | Delete | Delete | Tidak ke KDS
7071048 | NGMP JUNIOR + SOSRO | 19 | NGMP Jr+SOSRO | 13 | NGMP Jr+TS | 10 | 70 | #REF! | 71 | #REF! | 11 | #REF! |  | 5 Menit |  |  |  | #REF! |  |  | X | X | X | Delete | Delete | Delete | Delete | Delete | X | X | X | X | X | X | X | Delete | Delete | Tidak ke KDS
7071049 | NGMP JUNIOR + FRUIT PUNCH | 25 | NGMP Jr+FP | 10 |  | 0 | 70 | #REF! | 71 | #REF! | 11 | #REF! |  | 5 Menit | [6 empty] | X | X | X | Delete | Delete | Delete | Delete | Delete | X | X | X | X | X | X | X | Delete | Delete | Tidak ke KDS
7071050 | NGMB JUNIOR | 11 | NGMB Jr | 7 | NGMB Jr | 7 | 70 | #REF! | 71 | #REF! | 11 | #REF! | REBUSAN | 5 Menit | [6 empty] | X | X | X | Delete | Delete | Delete | Delete | Delete | X | X | X | X | X | X | X | Delete | Delete | Tidak ke KDS
7071051 | NGMB JUNIOR + AQUA 330 ML | 25 | NGMB Jr+AQUA | 12 | NGMB Jr+AQ | 10 | 70 | #REF! | 71 | #REF! | 11 | #REF! | REBUSAN | 5 Menit |  |  |  | #REF! |  |  | X | X | X | Delete | Delete | Delete | Delete | Delete | X | X | X | X | X | X | X | Delete | Delete | Tidak ke KDS
7071052 | NGMB JUNIOR + SOSRO | 19 | NGMB Jr+SOSRO | 13 | NGMB Jr+SO | 10 | 70 | #REF! | 71 | #REF! | 11 | #REF! | REBUSAN | 5 Menit |  |  |  | #REF! |  |  | X | X | X | Delete | Delete | Delete | Delete | Delete | X | X | X | X | X | X | X | Delete | Delete | Tidak ke KDS
8081100 | = EKSTRA MAKAN = | 16 | = EKSTRA MAKAN = | 16 |  | 0 | 80 | #REF! | 81 | #REF! |  | #REF!
8081101 | * XTRA SAMBAL * | 15 | * XTRA SAMBAL * | 15 | +SAMBAL* | 8 | 80 | #REF! | 81 | #REF! | 13 | #REF! |  |  |  |  | To be confirm u/ dicharge by OPS
8081102 | * XTRA KUAH * | 13 | * XTRA KUAH * | 13 | +KUAH* | 6 | 80 | #REF! | 81 | #REF! | 13 | #REF! |  |  |  |  | To be confirm u/ dicharge by OPS
8081103 | * XTRA SAOS * | 13 | * XTRA SAOS * | 13 | +SAOS* | 6 | 80 | #REF! | 81 | #REF! | 13 | #REF! |  |  |  |  | To be confirm u/ delete by OPS
8081104 | * XTRA SAOS PG * | 16 | * XTRA SAOS PG * | 16 | +SAOS PG* | 9 | 80 | #REF! | 81 | #REF! | 13 | #REF! |  |  |  |  | To be confirm u/ dicharge by OPS
8081105 | * XTRA ACAR * | 13 | * XTRA ACAR * | 13 | +ACAR* | 6 | 80 | #REF! | 81 | #REF! | 13 | #REF!
8081106 | *XTRA KECAP ASIN | 16 | * XTRA KECAP ASIN * | 19 | +KECAP ASIN* | 12 | 80 | #REF! | 81 | #REF! | 13 | #REF! |  |  |  |  | To be confirm u/ delete by OPS
8081107 | *XTRA KECAP MNS* | 16 | * XTRA KECAP MNS * | 18 | +KECAP MNS* | 11 | 80 | #REF! | 81 | #REF! | 13 | #REF! |  |  |  |  | To be confirm u/ delete by OPS
8081108 | * CABE POTONG * | 15 | * CABE POTONG * | 15 | CABE POTONG* | 12 | 80 | #REF! | 81 | #REF! | 13 | #REF! |  |  |  |  | To be confirm u/ delete by OPS
8081109 | * XTRA CUKA * | 13 | * XTRA CUKA * | 13 | +CUKA* | 6 | 80 | #REF! | 81 | #REF! | 13 | #REF! |  |  |  |  | To be confirm u/ delete by OPS
8082000 | == KEMASAN == | 13 | == KEMASAN == | 13 |  | 0 | 80 | #REF! | 82 | #REF! |  | #REF!
8082101 | * RINGKAS * | 11 | * RINGKAS * | 11 | RINGKAS* | 8 | 80 | #REF! | 82 | #REF! | 13 | #REF! |  |  |  |  | To be confirm u/ delete by OPS
8082102 | * ALAS PLASTIK * | 16 | * ALAS PLASTIK * | 16 | ALAS PLASTIK* | 13 | 80 | #REF! | 82 | #REF! | 13 | #REF! |  |  |  |  | To be confirm u/ delete by OPS
8082103 | * PLATSIK DULU * | 16 | * PLDL * | 8 | PDPL* |  | 80 | #REF! | 82 | #REF! | 13 | #REF!
8082105 | *BOX DINAMAKAN * | 16 | *BOX DINAMAKAN * | 16 | BOX DINAMAKAN* | 14 | 80 | #REF! | 82 | #REF! | 13 | #REF! |  |  |  |  | To be confirm u/ delete by OPS
8082106 | * SEMUA PISAH * | 15 | * SEMUA PISAH * | 15 | SEMUA PISAH* | 12 | 80 | #REF! | 82 | #REF! | 13 | #REF!
8083000 | = BAHAN MAKANAN= | 16 | = BAHAN MAKANAN= | 16 |  | 0 | 80 | #REF! | 83 | #REF! |  | #REF!
8083101 | * TDK JAMUR * | 13 | * TDK JAMUR * | 13 | T JAMUR* | 8 | 80 | #REF! | 83 | #REF! | 13 | #REF! |  |  |  |  | To be confirm u/ delete by OPS
8083102 | * TDK SAYUR * | 13 | * TDK SAYUR * | 13 | T SAYUR* | 8 | 80 | #REF! | 83 | #REF! | 13 | #REF!
8083103 | * TDK CAISIM * | 14 | * TDK CAISIM * | 14 | T CAISIM* | 9 | 80 | #REF! | 83 | #REF! | 13 | #REF!
8083104 | * TDK K.KOL * | 13 | * TDK K.KOL * | 13 | T K.KOL* | 8 | 80 | #REF! | 83 | #REF! | 13 | #REF!
8083105 | * TDK KOL * | 11 | * TDK KOL * | 11 | T KOL* | 6 | 80 | #REF! | 83 | #REF! | 13 | #REF!
8083106 | * TDK PECAI * | 13 | * TDK PECAI * | 13 | T PECAI* | 8 | 80 | #REF! | 83 | #REF! | 13 | #REF!
8083107 | * TDK WORTEL * | 14 | * TDK WORTEL * | 14 | T WORTEL* | 9 | 80 | #REF! | 83 | #REF! | 13 | #REF!
8083108 | * TDK DAUN BAWANG * | 19 | * TDK D.B. * | 12 | T D.BAWANG* | 11 | 80 | #REF! | 83 | #REF! | 13 | #REF!
8083109 | * TDK CABE MRH * | 16 | * TDK CABE MRH * | 16 | T CABE MRH* | 11 | 80 | #REF! | 83 | #REF! | 13 | #REF!
8083110 | *TDK CABE HIJAU* | 16 | *TDK CABE HIJAU* | 16 | T CABE HJAU* | 12 | 80 | #REF! | 83 | #REF! | 13 | #REF!
8083111 | *TDK BASO IKAN * | 16 | *TDK BASO IKAN * | 16 | T BASO IKAN* | 12 | 80 | #REF! | 83 | #REF! | 13 | #REF!
8083112 | * TDK UDANG * | 13 | * TDK UDANG * | 13 | T UDANG* | 8 | 80 | #REF! | 83 | #REF! | 13 | #REF!
8083113 | * TDK AYAM * | 12 | * TDK AYAM * | 12 | T AYAM* | 7 | 80 | #REF! | 83 | #REF! | 13 | #REF!
8083114 | * TDK TELUR * | 13 | * TDK TELUR * | 13 | T TELUR* | 8 | 80 | #REF! | 83 | #REF! | 13 | #REF!
8083115 | * TDK OTAK2 * | 13 | * TDK OTAK2 * | 13 | T OTAK2* | 8 | 80 | #REF! | 83 | #REF! | 13 | #REF!
8083116 | * TDK ISI * | 11 | * TDK ISI * | 11 | T ISI* | 6 | 80 | #REF! | 83 | #REF! | 13 | #REF!
8083117 | *ISI TELOR AJA * | 16 | *ISI TELOR AJA * | 16 | TELUR AJA* | 10 | 80 | #REF! | 83 | #REF! | 13 | #REF!
8083118 | *TDK BAWANG PUTIH * | 19 | *TDK BAWANG P. * | 16 | T BAWANG P.* | 12 | 80 | #REF! | 83 | #REF! | 13 | #REF!
8083119 | *ISI BASO IKAN SAJA | 19 | *ISI B.IKAN SAJA | 16 | B.IKAN SAJA* | 12 | 80 | #REF! | 83 | #REF! | 13 | #REF! |  |  |  |  | To be confirm u/ delete by OPS
8083120 | *ISI AYAM SAJA * | 16 | *ISI AYAM SAJA * | 16 | AYAM SAJA* | 10 | 80 | #REF! | 83 | #REF! | 13 | #REF! |  |  |  |  | To be confirm u/ delete by OPS
8083121 | *ISI UDANG SAJA* | 16 | *ISI UDANG SAJA* | 16 | UDANG SAJA* | 11 | 80 | #REF! | 83 | #REF! | 13 | #REF! |  |  |  |  | To be confirm u/ delete by OPS
8083122 | *TDK JAGUNG MD * | 16 | *TDK JAGUNG MD * | 16 | T JAGUNG MD* | 12 | 80 | #REF! | 83 | #REF! | 13 | #REF!
8083123 | * TDK BAWANG BOMBAY * | 21 | * TDK B. BOMB * | 15 | T BAWANG B.* | 12 | 80 | #REF! | 83 | #REF! | 13 | #REF!
8083124 | * TDK NANAS * | 13 | * TDK NANAS * | 13 | T NANAS* | 8 | 80 | #REF! | 83 | #REF! | 13 | #REF!
8083125 | *TDK SELEDRI* | 13 | *TDK SELEDRI* | 13 | T SELEDRI* | 10 | 80 | #REF! | 83 | #REF! | 13 | #REF! |  |  |  |  | To be confirm u/ delete by OPS
8083126 | *TDK BROKOLI* | 13 | *TDK BROKOLI* | 13 | T BROKOLI* | 10 | 80 | #REF! | 83 | #REF! | 13 | #REF!
8083127 | *TDK JAHE* | 10 | *TDK JAHE* | 10 | T JAHE* |  | 80 | #REF! | 83 | #REF! | 13 | #REF! |  |  |  |  | To be confirm u/ delete by OPS
8083128 | *TDK SAYUR CMP* | 15 | *TDK SAYUR CMP* | 15 | T SAYUR CMP* | 12 | 80 | #REF! | 83 | #REF! | 13 | #REF!
8083129 | *TDK SMOKED CHK* | 16 | *TDK SMOKED CHK* | 16 | T SMOKD CHK* | 12 | 80 | #REF! | 83 | #REF! | 13 | #REF!
8083130 | *TDK BWNG PTH GR | 16 | *TDK BWNG PTH GR | 16 | T BWG GR* | 9 | 80 | #REF! | 83 | #REF! | 13 | #REF!
8083201 | * TDK ES * | 10 | * TDK ES * | 10 |  |  | 80 | #REF! | 83 | #REF! | 13 | #REF!
8083202 | * SEDIKIT ES * | 14 | * SEDIKIT ES * | 14 |  | 0 | 80 | #REF! | 83 | #REF! |  | #REF!
8083203 | * TDK GULA * | 12 | * TDK GULA * | 12 |  | 0 | 80 | #REF! | 83 | #REF! |  | #REF!
8083204 | * SEDIKIT GULA * | 16 | * SEDIKIT GULA * | 16 |  | 0 | 80 | #REF! | 83 | #REF! |  | #REF!
8083205 | * GULA CAIR * | 13 | * GULA CAIR * | 13 |  | 0 | 80 | #REF! | 83 | #REF! |  | #REF!
8083206 | * GULA PASIR * | 14 | * GULA PASIR * | 14 |  | 0 | 80 | #REF! | 83 | #REF! |  | #REF!
8083209 | * ES TDK GULA * | 15 | * ES TDK GULA * | 15 |  | 0 | 80 | #REF! | 83 | #REF! |  | #REF!
8083210 | * + ES BATU * | 13 | * + ES BATU * | 13 |  | 0 | 80 | #REF! | 83 | #REF! |  | #REF!
8083211 | * TDK SS CKT * | 14 | * TDK SS CKT * | 14 |  | 0 | 80 | #REF! | 83 | #REF! |  | #REF!
8083212 | * TDK SS PTH * | 14 | * TDK SS PTH * | 14 |  | 0 | 80 | #REF! | 83 | #REF! |  | #REF!
8083213 | * + KACANG * | 12 | * + KACANG * | 12 |  | 0 | 80 | #REF! | 83 | #REF! |  | #REF!
8083214 | * TDK CAH JAMUR * | 17 | * TDK CJ * | 10 |  |  | 80 | #REF! | 83 | #REF! | 13 | #REF!
8083301 | * CP STRBERRY * | 15 | * CP STRBERRY * | 15 |  | 0 | 80 | #REF! | 83 | #REF! |  | #REF!
8083302 | * CP KOPYOR * | 13 | * CP KOPYOR * | 13 |  | 0 | 80 | #REF! | 83 | #REF! |  | #REF!
8083303 | * CP MELON * | 12 | * CP MELON * | 12 |  | 0 | 80 | #REF! | 83 | #REF! |  | #REF!
8083304 | * CP MANGGA * | 13 | * CP MANGGA * | 13 |  | 0 | 80 | #REF! | 83 | #REF! |  | #REF!
8083305 | * CP ALPOKAT * | 14 | * CP ALPOKAT * | 14 |  | 0 | 80 | #REF! | 83 | #REF! |  | #REF!
8083306 | * CP SEMANGKA * | 15 | * CP SEMANGKA * | 15 |  | 0 | 80 | #REF! | 83 | #REF! |  | #REF!
8083307 | * CP JAMBU * | 12 | * CP JAMBU * | 12 |  | 0 | 80 | #REF! | 83 | #REF! |  | #REF!
8083308 | * CP TOMAT * | 12 | * CP TOMAT * | 12 |  | 0 | 80 | #REF! | 83 | #REF! |  | #REF!
8083309 | * CP PEPAYA * | 13 | * CP PEPAYA * | 13 |  | 0 | 80 | #REF! | 83 | #REF! |  | #REF!
8083310 | * CP NANAS * | 12 | * CP NANAS * | 12 |  | 0 | 80 | #REF! | 83 | #REF! |  | #REF!
8083311 | * CP SIRSAK * | 13 | * CP SIRSAK * | 13 |  | 0 | 80 | #REF! | 83 | #REF! |  | #REF!
8084000 | = BUMBU = | 9 | = BUMBU = | 9 |  |  | 80 | #REF! | 84 | #REF! |  | #REF!
8084101 | * TDK MINYAK * | 14 | * TDK MINYAK * | 14 | T MINYAK* | 9 | 80 | #REF! | 84 | #REF! | 13 | #REF!
8084102 | * TDK BUMBU * | 13 | * TDK BUMBU * | 13 | T BUMBU* | 8 | 80 | #REF! | 84 | #REF! | 13 | #REF!
8084103 | * TAWAR * | 9 | * TAWAR * | 9 | TAWAR* | 6 | 80 | #REF! | 84 | #REF! | 13 | #REF!
8084104 | * SEDIKIT MINYAK | 16 | * SEDIKIT MINYAK | 16 | SDKT MNYAK* | 11 | 80 | #REF! | 84 | #REF! | 13 | #REF!
9000000 | == MESSAGES == | 14 | == MESSAGES == | 14 |  | 0 | 90 | #REF! | 91 | #REF! |  | #REF!
9091000 | = INFO = | 8 | = INFO = | 8 |  |  | 90 | #REF! | 91 | #REF! |  | #REF!
9091001 | *TAMBAH MAKANAN * | 17 | *TAMBAH MAKANAN * | 17 | *TAMBAH* | 8 | 90 | #REF! | 91 | #REF! | 13 | #REF!
9091002 | *TAMBAH MINUMAN * | 17 | *TAMBAH MINUMAN * | 17 | *TAMBAH MINUMAN * | 17 | 90 | #REF! | 91 | #REF! | 13 | #REF!
9091003 | * PATAS MAKANAN * | 17 | * PATAS MAKANAN * | 17 | * PATAS * | 9 | 90 | #REF! | 91 | #REF! | 13 | #REF!
9091004 | * PATAS MINUMAN * | 17 | * PATAS MINUMAN * | 17 | * PATAS MINUMAN * | 17 | 90 | #REF! | 91 | #REF! | 13 | #REF!
9091005 | * BUKA PUASA * | 14 | * BUKA PUASA * | 14 | * BUKA PUASA * | 14 | 90 | #REF! | 91 | #REF! | 13 | #REF!
9091006 | * ROMBONGAN * | 13 | * ROMBONGAN * | 13 | * ROMBONGAN * | 13 | 90 | #REF! | 91 | #REF! | 13 | #REF!
9091007 | * ULTAH * | 9 | * ULTAH * | 9 | * ULTAH * |  | 90 | #REF! | 91 | #REF! | 13 | #REF!
9091008 | * TOD * | 7 | * TOD * | 7 | * TOD * |  | 90 | #REF! | 91 | #REF! | 13 | #REF!
9091009 | * PINGGIR * | 11 | * PINGGIR * | 11 | * PINGGIR * | 11 | 90 | #REF! | 91 | #REF! | 13 | #REF!
9091010 | * TENGAH * | 10 | * TENGAH * | 10 | * TENGAH * |  | 90 | #REF! | 91 | #REF! | 13 | #REF!
9092000 | = PROSES = | 10 | = PROSES = | 10 |  |  | 90 | #REF! | 92 | #REF! |  | #REF!
9092001 | PISAH | 5 | * PISAH * | 9 | * PISAH * | 9 | 90 | #REF! | 92 | #REF! | 13 | #REF!
9092002 | YAMIN | 5 | * YAMIN * | 9 | * YAMIN * | 9 | 90 | #REF! | 92 | #REF! | 13 | #REF!
9092003 | GORENG | 6 | * GORENG * | 10 | * GORENG * |  | 90 | #REF! | 92 | #REF! | 13 | #REF!
9092201 | HANGAT | 6 | * HANGAT * | 10 |  |  | 90 | #REF! | 92 | #REF! | 13 | #REF!
9092202 | PANAS | 5 | * PANAS * | 9 |  |  | 90 | #REF! | 92 | #REF! | 13 | #REF!
9092203 | BIASA | 5 | * BIASA * | 9 |  |  | 90 | #REF! | 92 | #REF! | 13 | #REF!
9092204 | ES DIPISAH | 10 | * ES DIPISAH * | 14 |  | 0 | 90 | #REF! | 92 | #REF! | 13 | #REF!
9092205 | TEH DIPISAH | 11 | * TEH DIPISAH * | 15 |  | 0 | 90 | #REF! | 92 | #REF! | 13 | #REF!
9092206 | GULA PISAH | 10 | * GULA PISAH * | 14 |  | 0 | 90 | #REF! | 92 | #REF! | 13 | #REF!
9092207 | GELAS BESAR | 11 | * GELAS BESAR * | 15 |  | 0 | 90 | #REF! | 92 | #REF! | 13 | #REF!
9092208 | KASAR | 5 | * KASAR * | 9 |  |  | 90 | #REF! | 92 | #REF! | 13 | #REF!
9099999 | PRINTER OK..!!! | 15 | PRINTER OK..!!! | 15 | PRINTER OK..!!! | 15 | 90 | #REF! | 91 | #REF! |  | #REF!

## Master Data Paket
Number (PLU) | Complete Name (Max 25 chars) | Length Complete name | Name 1 (Max 16 chars) | Length Alias Name | Name 2 (Max 6 chars) | Length KDS Display | mg | Major Grop | fg | Family Group | rg | Report Group | Printer | KDS Colour | Priority | Item Line Group | Notes | Tray Requirement | Refrensi Hal | Wadah | Tray
7072001 | PAKET PADU 1 | 12 | PKT PADU 1 | 10 | PADU 1 |  | 70 | PROMOTION | 71 | PROMO | 13 | REBUSAN & GORENGAN | REB&GOR
7072002 | PAKET PADU 2 | 12 | PKT PADU 2 | 10 | PADU 2 |  | 70 | PROMOTION | 71 | PROMO | 13 | REBUSAN & GORENGAN | REB&GOR | [8 empty] | REBUSAN
7072003 | PAKET PADU 3 | 12 | PKT PADU 3 | 10 | PADU 3 |  | 70 | PROMOTION | 71 | PROMO | 13 | REBUSAN & GORENGAN | REB&GOR | [8 empty] | GORENGAN
7072004 | PAKET PADU 4 | 12 | PKT PADU 4 | 10 | PADU 4 |  | 70 | PROMOTION | 71 | PROMO | 13 | REBUSAN & GORENGAN | REB&GOR | [8 empty] | REB&GOR
7072008 | PAKET BERKAT 1 | 14 | PKT BERKAT 1 | 12 | BERKAT 1 | 8 | 70 | PROMOTION | 71 | PROMO | 13 | REBUSAN & GORENGAN | REBUSAN
7072009 | PAKET BERKAT 2 | 14 | PKT BERKAT 2 | 12 | BERKAT 2 | 8 | 70 | PROMOTION | 71 | PROMO | 13 | REBUSAN & GORENGAN | REB&GOR
7072010 | PAKET BERKAT 3 | 14 | PKT BERKAT 3 | 12 | BERKAT 3 | 8 | 70 | PROMOTION | 71 | PROMO | 13 | REBUSAN & GORENGAN | REBUSAN
7072011 | PAKET BERKAT 4 | 14 | PKT BERKAT 4 | 12 | BERKAT 4 | 8 | 70 | PROMOTION | 71 | PROMO | 13 | REBUSAN & GORENGAN | REBUSAN
7072028 | PAKET SALJU 1 | 13 | PKT SALJU 1 | 11 | SALJU 1 | 7 | 70 | PROMOTION | 71 | PROMO | 13 | REBUSAN & GORENGAN | REB&GOR
7072029 | PAKET SALJU 2 | 13 | PKT SALJU 2 | 11 | SALJU 2 | 7 | 70 | PROMOTION | 71 | PROMO | 13 | REBUSAN & GORENGAN | REB&GOR
7072030 | PAKET SALJU 3 | 13 | PKT SALJU 3 | 11 | SALJU 3 | 7 | 70 | PROMOTION | 71 | PROMO | 13 | REBUSAN & GORENGAN | REB&GOR
7072074 | FIELDTRIP 1 | 11 | FIELDTRIP1 | 10 | FIELDTRIP1 |  | 70 | PROMOTION | 71 | PROMO | 13 | REBUSAN & GORENGAN | REBUSAN
7072075 | FIELDTRIP 2 | 11 | FIELDTRIP2 | 10 | FIELDTRIP2 |  | 70 | PROMOTION | 71 | PROMO | 13 | REBUSAN & GORENGAN | REBUSAN
7072082 | PAKET BARTER A | 14 | PKT BARTER A | 12 | PKT A | 8 | 70 | PROMOTION | 71 | PROMO | 13 | REBUSAN & GORENGAN | REBUSAN
7072083 | PAKET BARTER B | 14 | PKT BARTER B | 12 | PKT B | 8 | 70 | PROMOTION | 71 | PROMO | 13 | REBUSAN & GORENGAN | REB&GOR
7072084 | PAKET BARTER C | 14 | PKT BARTER C | 12 | PKT C | 8 | 70 | PROMOTION | 71 | PROMO | 13 | REBUSAN & GORENGAN | REB&GOR
7072092 | BREAKFAST 1 | 11 | BREAKFAST 1 | 11 | BREAKFAST1 | 10 | 70 | PROMOTION | 71 | PROMO | 13 | REBUSAN & GORENGAN | REB&GOR
7072093 | BREAKFAST 2 | 11 | BREAKFAST 2 | 11 | BREAKFAST2 | 10 | 70 | PROMOTION | 71 | PROMO | 13 | REBUSAN & GORENGAN | REB&GOR
7072094 | BREAKFAST 3 | 11 | BREAKFAST 3 | 11 | BREAKFAST3 | 10 | 70 | PROMOTION | 71 | PROMO | 13 | REBUSAN & GORENGAN | REB&GOR
7072095 | BREAKFAST 4 | 11 | BREAKFAST 4 | 11 | BREAKFAST4 | 10 | 70 | PROMOTION | 71 | PROMO | 13 | REBUSAN & GORENGAN | REB&GOR
7072111 | LSP 1 | 5 | LSP 1 | 5 | LSP 1 |  | 70 | PROMOTION | 71 | PROMO | 13 | REBUSAN & GORENGAN | REB&GOR
7072112 | LSP 2 | 5 | LSP 2 | 5 | LSP 2 |  | 70 | PROMOTION | 71 | PROMO | 13 | REBUSAN & GORENGAN | REB&GOR
7072113 | LSP 3 | 5 | LSP 3 | 5 | LSP 3 |  | 70 | PROMOTION | 71 | PROMO | 13 | REBUSAN & GORENGAN | REB&GOR
7072114 | LSP 4 | 5 | LSP 4 | 5 | LSP 4 |  | 70 | PROMOTION | 71 | PROMO | 13 | REBUSAN & GORENGAN | REB&GOR
7072115 | LSP 5 | 5 | LSP 5 | 5 | LSP 5 |  | 70 | PROMOTION | 71 | PROMO | 13 | REBUSAN & GORENGAN | REB&GOR
7072116 | LSP 6 | 5 | LSP 6 | 5 | LSP 6 |  | 70 | PROMOTION | 71 | PROMO | 13 | REBUSAN & GORENGAN | REB&GOR
7072117 | LSP 7 | 5 | LSP 7 | 5 | LSP 7 |  | 70 | PROMOTION | 71 | PROMO | 13 | REBUSAN & GORENGAN | REB&GOR
7072118 | LSP 8 | 5 | LSP 8 | 5 | LSP 8 |  | 70 | PROMOTION | 71 | PROMO | 13 | REBUSAN & GORENGAN | REB&GOR
7072119 | LSP 9 | 5 | LSP 9 | 5 | LSP 9 |  | 70 | PROMOTION | 71 | PROMO | 13 | REBUSAN & GORENGAN | REB&GOR
7072120 | LSP 10 | 6 | LSP 10 | 6 | LSP 10 |  | 70 | PROMOTION | 71 | PROMO | 13 | REBUSAN & GORENGAN | REB&GOR
7072121 | LSP 11 | 6 | LSP 11 | 6 | LSP 11 |  | 70 | PROMOTION | 71 | PROMO | 13 | REBUSAN & GORENGAN | REB&GOR
7072122 | LSP 12 | 6 | LSP 12 | 6 | LSP 12 |  | 70 | PROMOTION | 71 | PROMO | 13 | REBUSAN & GORENGAN | REB&GOR
7072132 | PROMO TSEL | 10 | PROMO TSEL | 10 | PROMO TSEL |  | 70 | PROMOTION | 71 | PROMO | 13 | REBUSAN & GORENGAN | GORENGAN
7072134 | PAKET BARTER D | 14 | PKT BARTER D | 12 | BARTER D | 8 | 70 | PROMOTION | 71 | PROMO | 13 | REBUSAN & GORENGAN | REB&GOR
7072135 | PAKET BARTER E | 14 | PKT BARTER E | 12 | BARTER E | 8 | 70 | PROMOTION | 71 | PROMO | 13 | REBUSAN & GORENGAN | REB&GOR
7072136 | PAKET BARTER F | 14 | PKT BARTER F | 12 | BARTER F | 8 | 70 | PROMOTION | 71 | PROMO | 13 | REBUSAN & GORENGAN | REB&GOR
7072140 | PAKET BARTER G | 14 | PKT BARTER G | 12 | BARTER G | 8 | 70 | PROMOTION | 71 | PROMO | 13 | REBUSAN & GORENGAN | REB&GOR
7072141 | PAKET BARTER H | 14 | PKT BARTER H | 12 | BARTER H | 8 | 70 | PROMOTION | 71 | PROMO | 13 | REBUSAN & GORENGAN | REB&GOR
7072142 | PAKET BARTER I | 14 | PKT BARTER I | 12 | BARTER I | 8 | 70 | PROMOTION | 71 | PROMO | 13 | REBUSAN & GORENGAN | REB&GOR
7072143 | PAKET BARTER J | 14 | PKT BARTER J | 12 | BARTER J | 8 | 70 | PROMOTION | 71 | PROMO | 13 | REBUSAN & GORENGAN | REB&GOR
7072144 | PAKET BARTER K | 14 | PKT BARTER K | 12 | BARTER K | 8 | 70 | PROMOTION | 71 | PROMO | 13 | REBUSAN & GORENGAN | REB&GOR
7072145 | PAKET BARTER L | 14 | PKT BARTER L | 12 | BARTER L | 8 | 70 | PROMOTION | 71 | PROMO | 13 | REBUSAN & GORENGAN | REB&GOR
7072146 | PAKET BARTER M | 14 | PKT BARTER M | 12 | BARTER M | 8 | 70 | PROMOTION | 71 | PROMO | 13 | REBUSAN & GORENGAN | REB&GOR
7072147 | PAKET BARTER N | 14 | PKT BARTER N | 12 | BARTER N | 8 | 70 | PROMOTION | 71 | PROMO | 13 | REBUSAN & GORENGAN | REB&GOR
7072148 | PAKET BARTER O | 14 | PKT BARTER O | 12 | BARTER O | 8 | 70 | PROMOTION | 71 | PROMO | 13 | REBUSAN & GORENGAN | REB&GOR
7072149 | PAKET BARTER P | 14 | PKT BARTER P | 12 | BARTER P | 8 | 70 | PROMOTION | 71 | PROMO | 13 | REBUSAN & GORENGAN | REB&GOR
7072164 | REWARD A | 8 | RWD-A | 5 | RWD-A |  | 70 | PROMOTION | 71 | PROMO | 13 | REBUSAN & GORENGAN | REB&GOR
7072165 | REWARD B | 8 | RWD-B | 5 | RWD-B |  | 70 | PROMOTION | 71 | PROMO | 13 | REBUSAN & GORENGAN | REB&GOR
7072166 | REWARD C | 8 | RWD-C | 5 | RWD-C |  | 70 | PROMOTION | 71 | PROMO | 13 | REBUSAN & GORENGAN | REB&GOR
7072167 | REWARD D | 8 | RWD-D | 5 | RWD-D |  | 70 | PROMOTION | 71 | PROMO | 13 | REBUSAN & GORENGAN | GORENGAN
7072173 | REWARD E | 8 | RWD-E | 5 | RWD-E |  | 70 | PROMOTION | 71 | PROMO | 13 | REBUSAN & GORENGAN | REBUSAN
7072174 | REWARD F | 8 | RWD-F | 5 | RWD-F |  | 70 | PROMOTION | 71 | PROMO | 13 | REBUSAN & GORENGAN | REBUSAN
7072175 | PAKET 17-8-45 | 13 | PKT 17-8-45 | 11 | 17-8-45 | 7 | 70 | PROMOTION | 71 | PROMO | 13 | REBUSAN & GORENGAN | GORENGAN
7072176 | PKT TAMBAH 15RB |  | PKT TAMBAH 15RB |  | PKT TAMBAH 15RB | [7 empty] | GORENGAN
7072177 | PAKET GOTU BAKMI |  | PAKET GOTU BAKMI |  | PAKET GOTU BAKMI | [7 empty] | REB&GOR
7072178 | PAKET GOTU NASI |  | PAKET GOTU NASI |  | PAKET GOTU NASI | [7 empty] | REB&GOR
7072179 | REWARD G | 8 | RWD-G | 5 | RWD-G |  | 70 | PROMOTION | 71 | PROMO | 13 | REBUSAN & GORENGAN | REBUSAN
7072180 | REWARD H | 8 | RWD-H | 5 | RWD-H |  | 70 | PROMOTION | 71 | PROMO | 13 | REBUSAN & GORENGAN
7072181 | KUPON DSO A | 11 | KUPON DSO A | 11 | DSO A | 9 | 70 | PROMOTION | 71 | PROMO | 13 | REBUSAN & GORENGAN | REBUSAN
7072182 | KUPON DSO B | 11 | KUPON DSO B | 11 | DSO B | 9 | 70 | PROMOTION | 71 | PROMO | 13 | REBUSAN & GORENGAN | GORENGAN
7072183 | PAKET SALJU 1 UP | 16 | PKT SALJU 1 UP | 14 | SALJU 1 UP | 10 | 70 | PROMOTION | 71 | PROMO | 13 | REBUSAN & GORENGAN | REB&GOR
7072184 | PAKET SALJU 2 UP | 16 | PKT SALJU 2 UP | 14 | SALJU 2 UP | 10 | 70 | PROMOTION | 71 | PROMO | 13 | REBUSAN & GORENGAN | REB&GOR
7072185 | PAKET SALJU 3 UP | 16 | PKT SALJU 3 UP | 14 | SALJU 3 UP | 10 | 70 | PROMOTION | 71 | PROMO | 13 | REBUSAN & GORENGAN | REB&GOR
7072186 | PKT 20160 |  | PKT 20160 |  | PKT 20160 | [7 empty] | REBUSAN
7072187 | KUPON DSO C |  | KUPON DSO C |  | DSO C | [7 empty] | GORENGAN
7072150 | PKT LDF-1 |  | PKT LDF-1 | PKT LDF-1 | LDF-1 | [7 empty] | REBUSAN
7072151 | PKT LDF-2 |  | PKT LDF-2 | PKT LDF-2 | LDF-2 | [7 empty] | REB&GOR
7072188 | PKT LDF-3 |  | PKT LDF-3 |  | LDF-3 | [7 empty] | REBUSAN
7072189 | PKT LDF-4 |  | PKT LDF-4 |  | LDF-4 | [7 empty] | GORENGAN
7072190 | PKT LDF-5 |  | PKT LDF-5 |  | LDF-5 | [7 empty] | REBUSAN
7072191 | PKT LDF-6 |  | PKT LDF-6 |  | LDF-6 | [7 empty] | REBUSAN
7072192 | PKT LDF-7 |  | PKT LDF-7 |  | LDF-7 | [7 empty] | REBUSAN
7072193 | PKT LDF-8 |  | PKT LDF-8 |  | LDF-8 | [7 empty] | REBUSAN
7072194 | EMPLOYEE MEAL |  | EMPLOYEE MEAL |  | EMPLOYEE MEAL | [7 empty] | REB&GOR
7072195 | TAMBAH 30RB-A |  | TAMBAH 30RB-A |  | TAMBAH 30RB-A | [7 empty] | GORENGAN
7072196 | TAMBAH 30RB-B |  | TAMBAH 30RB-B |  | TAMBAH 30RB-B | [7 empty] | GORENGAN
7072197 | TAMBAH 35RB-A |  | TAMBAH 35RB-A |  | TAMBAH 35RB-A
7072198 | TAMBAH 35RB-B |  | TAMBAH 35RB-B |  | TAMBAH 35RB-B
7072199 | TAMBAH 35RB-C |  | TAMBAH 35RB-C |  | TAMBAH 35RB-C
7072200 | TSEL ½ PG |  | TSEL ½ PG |  | TSEL ½ PG | [7 empty] | GORENGAN
7072201 | PROMO ULTAH KAL |  | PROMO ULTAH KAL |  | PROMO ULTAH KAL | [7 empty] | REBUSAN
7072202 | BARTER NASI GM |  | BARTER NASI GM |  | BARTER NASI GM | [7 empty] | REBUSAN
7072203 | BARTER NASI GR |  | BARTER NASI GR |  | BARTER NASI GR | [7 empty] | GORENGAN
7072204 | BARTER ST MANIS |  | BARTER ST MANIS |  | BARTER ST MANIS
7072205 | FREE LEMON ST |  | FREE LEMON ST |  | FREE LEMON ST
7072206 | KUPON ½ PG |  | KUPON ½ PG |  | KUPON ½ PG | [7 empty] | GORENGAN
7072207 | PAS 1 |  | PAS 1 |  | PAS 1 | [7 empty] | GORENGAN
7072208 | PAS 2 |  | PAS 2 |  | PAS 2 | [7 empty] | GORENGAN
7072209 | PAS 3 |  | PAS 3 |  | PAS 3 | [7 empty] | GORENGAN
7072210 | FREE MENU MANDIRI |  | FREE MENU MANDIRI |  | FREE MENU MANDIRI
7072211 | VCR PWP BTS |  | VCR PWP BTS |  | VCR PWP BTS | [7 empty] | GORENGAN
7072212 | VCR PWP TSEL BTS |  | VCR PWP TSEL BTS |  | VCR PWP TSEL BTS | [7 empty] | GORENGAN
7072213 | BXC PRIVILLAGE |  | BXC PRIVILLAGE |  | BXC PRIVILLAGE | [7 empty] | GORENGAN
7072214 | FREE CITIBANK |  | FREE CITIBANK |  | FREE CITIBANK | [7 empty] | REB&GOR
7072215 | FREE BCA |  | FREE BCA |  | FREE BCA | [7 empty] | GORENGAN
7072216 | KUPON GRATIS |  | KUPON GRATIS |  | KUPON GRATIS | [7 empty] | GORENGAN
7072217 | QUICK WIN FREE |  | QUICK WIN FREE |  | QUICK WIN FREE | [7 empty] | GORENGAN
7072218 | PROMO FRUITILALA |  | PROMO FRUITILALA |  | PROMO FRUITILALA
7072219 | FREE BNI |  | FREE BNI |  | FREE BNI | [7 empty] | GORENGAN
7072220 | PROMO KUPON KAL |  | PROMO KUPON KAL |  | PROMO KUPON KAL
7072221 | VCR FRUITILALA |  | VCR FRUITILALA |  | VCR FRUITILALA
7072222 | PKT LDF-9 |  | PKT LDF-9 |  | LDF-9 | [7 empty] | GORENGAN
7072223 | PKT LDF-10 |  | PKT LDF-10 |  | LDF-10 | [7 empty] | REB&GOR
7072224 | PKT LDF-11 |  | PKT LDF-11 |  | LDF-11 | [7 empty] | REBUSAN